## Estimate v1
WordPress: | 360
1. Core Theme
2. Post
3. Interest Page | 200
4. 404
5. Archive
6. Author
7. Plugins:
o Google Analytics
o SiteMaps
Users:
1. Moderator-LDAP /WP-Admin (Internal Users) | 300
· LDAP Plugin
· Badges-by role, user-meta
· User image
· Moderator Dashboard
· Routing (Taxonomy)
2. External User- | 600
SSO: | 500
· Create user
· Create via fb
· Log in
· Log in via Fb
Feature:
· Comment | 50
Profile | 50
Q&A: | 800
· Syndication | 500
· Prototype Via Json API, post etc
· Vote on Q/A-anonymous (AJAX) | 50
· Follow Categories or question or tag | 50
· Ask questions | 100
· Answer questions or comment on answer (goes to moderator) | 100
Content Migration | 500
Search: | 100
Responsys | 100
Login and Registration | 100
Homepage | 100
Total: | 2960 | 82.2222
10
36
360
FED Hours | 980

## Estimate v2
|  | Total points | 174 |  |  |  | Hours per point |  |  |  | weeks | 12 |  |  | Our Points |  | Estimated Points
[7 empty] | Low | Hi |  |  | week hours | 36 |  |  | Point | Hours | Points | Hours
|  | Total Hrs (High) | 5568 |  | Best quality |  | 16 | 32 |  |  | Total Hours | 432 |  |  | 1 | 4 | 1 | 16
|  | Total Hrs (Average) | 4176 |  | Moderate | [5 empty] | low | 2080 | 4.8148 |  | 2 | 8 | 2 | 32
|  | Total Hrs Low) | 2784 |  | Aggressive | [5 empty] | high | 4160 | 9.6296 |  | 3 | 16 | 3 | 48
[15 empty] | 5 | 30 | 4 | 64
[15 empty] | 8 | 40 | 5 | 80
[11 empty] | average | 3120 | 7.2222 |  |  |  | 12 weeks | 4 weeks
Track Total Hours
LOE in Hours Calculated
Req # | Story # | Epic | User Story |  | Track |  | Points | Low | High | Average | UX Priority | Eng Priority | Dependency | Notes |  |  | Low | High | High | High | High |  | Low | Low | Low | Low | Low |  | Avg | Avg | Avg | Avg | Avg
|  |  |  | Possible solution |  | Our Points | [10 empty] | 1 | 2 | 3 | 4 | 5 |  | 1 | 2 | 3 | 4 | 5 |  | 1 | 2 | 3 | 4 | 5
| 1 | Community Site | Home page - Logged in/Logged out(Hero image, articles, QA activity, Twitter feed, total members) |  | 1 |  | 8 | 128 | 256 | 192 | 1 | [5 empty] | 128 | 0 | 0 | 0 | 0 |  | 128 | 0 | 0 | 0 | 0 |  | 192 | 0 | 0 | 0 | 0
| 1.1 | Community Site | Community Header |  |  | 3
| 1.2 | Community Site | Community Global Navigation | WP Menus |  | 3 |  | 128
|  | Home Page | See all Experts (we are here to help) | http://blog.fitstudio.com/ - Blog Contributors |  | 3
|  | Home Page | Featured Blog | FA Lite - plugin |  | 3
|  | Home Page | Ask A Question | custom |  | 5
|  | Home Page | Featured Q&A | Widget by categories |  | 3
|  | Home Page | Poll of the week | Iteration 4 |  | 0
|  | Home Page | Add Unit | CQ5, iteration 4 |  | 0
|  | Home Page | Recent Activity | by asking, answering and following content |  | 3
| 1.3 | Community Site | Community Footer
Tim |  | Home Page | FED
| 2 | Community Site | Q & A (discussions) |  | 1 |  | 8 | 128 | 0 | 64 | 2 |  |  | (CPT) Custom Post Type post_type=question as a parent parent_post=0. (CPT) post_type=answer, parent_post={questionID} |  |  | 128 | 0 | 0 | 0 | 0 |  | 128 | 0 | 0 | 0 | 0 |  | 64 | 0 | 0 | 0 | 0
Eddie |  | Q And A | Architect | wp_posts.post_type index field for searching |  | 2
|  | Q And A | Question = Post | SSO users are asking questions |  | 3
|  | Q And A | Comment = Answer | Nesting comments |  | 3
Tim |  | Q And A | FED
| 3 | Community Site | Blog |  | 1 |  | 3 | 48 | 96 | 72 | 1 |  |  | templates = single, archive, aside for video |  |  | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
|  |  | 404 |  |  | 3
|  |  | Archvie | Includes, tags, category, search results |  | 3
|  |  | Single |  |  | 3
|  |  | Page | This goes to interest and customer service |  | 0
| 4 | Community Site | User profile page (My discussions, photo, Interests, badges) |  | 1 |  | 5 | 80 | 160 | 120 | 2 | [5 empty] | 80 | 0 | 0 | 0 | 0 |  | 80 | 0 | 0 | 0 | 0 |  | 120 | 0 | 0 | 0 | 0
Jason |  | User Profile | Dashboard |  |  | 5
Jason |  | User Profile | My Discussions & Answers |  |  | 3
Jason |  | User Profile | My Following |  |  | 3
Jason |  | User Profile | Change My Setting | Unfollow and stopping emails |  | 2
Jason |  | User Profile | My Votes |  |  | 2
Jason |  | User Profile | My Flags
FED
| 5 | Community Site | User Admin Settings Page |  | 1 | 8 | 3 | 48 | 96 | 72 | 4 |  |  | Place where they can turn off (opt-out) of following |  |  | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
| 6 | Community Site | Articles (Guides) |  | 1 | 3 | 2 | 32 | 64 | 48 | 3 | [5 empty] | 32 | 0 | 0 | 0 | 0 |  | 32 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0
| 7 | Community Site | Ad units on pages |  | 4 | 16 | 5 | 80 | 160 | 120 | 0 |  |  | Use CQ5 |  |  | 0 | 0 | 0 | 160 | 0 |  | 0 | 0 | 0 | 80 | 0 |  | 0 | 0 | 0 | 120 | 0
| 8 | Community Site | Site search (discussions, articles, blogs) |  | 1 | 8 | 3 | 48 | 96 | 72 | 3 |  |  | Indexing of blog and store pages is new addition. |  |  | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
| 9 | Community Site | Site Search - Auto Complete |  | 5 |  | 8 | 128 | 256 | 192 | 0 |  |  | will require mongo DB |  |  | 0 | 0 | 0 | 0 | 256 |  | 0 | 0 | 0 | 0 | 128 |  | 0 | 0 | 0 | 0 | 192
|  |  | Mongo DB setup |  |  | 8
|  |  | Code Integration |  |  | 8
|  |  | Jquery - FED |  |  | 8
|  |  | Stress testing |  |  | 3
| 10 | Community Site
|  | Login | SSO |  | 1 | 8 | 5 | 80 | 160 | 120 | 0 |  |  | Profile/SSO will take care of validating and authenticating open id just like user/password |  |  | 80 | 0 | 0 | 0 | 0 |  | 80 | 0 | 0 | 0 | 0 |  | 120 | 0 | 0 | 0 | 0
|  | Login | Login/ Logout |  |  | 3
|  | Login | Open ID - Facebook |  |  | 5
|  | Login | Create Login |  |  | 5
|  | Login | Integration / Security |  |  | 3
| 11 | Community Site |  |  | 1 |  | 5 | 80 | 160 | 120 | 2 | [5 empty] | 80 | 0 | 0 | 0 | 0 |  | 80 | 0 | 0 | 0 | 0 |  | 120 | 0 | 0 | 0 | 0
|  | Login | User Login |  |  | 2
|  | Login | Login/ Logout |  |  | 2
Sebastian | 12 | Community Site | Feedback (Qualtrics) |  | 3 | 5 | 1 | 16 | 32 | 24 | 0 | [5 empty] | 0 | 0 | 32 | 0 | 0 |  | 0 | 0 | 16 | 0 | 0 |  | 0 | 0 | 24 | 0 | 0
Tim/Jason | 13 | Community Site | Contacts page |  | 1 | 3 | 1 | 16 | 32 | 24 | 5 | [5 empty] | 16 | 0 | 0 | 0 | 0 |  | 16 | 0 | 0 | 0 | 0 |  | 24 | 0 | 0 | 0 | 0
| 14 | Community Site | Tag/filter content |  | 1 |  | 8 | 128 | 256 | 192 | 2 |  |  | Separate installation for each site. Double UX work |  |  | 128 | 0 | 0 | 0 | 0 |  | 128 | 0 | 0 | 0 | 0 |  | 192 | 0 | 0 | 0 | 0
| 15 | User Profile | Activity feed based on profile |  | 1 | 8 | 3 | 48 | 96 | 72 | 0 |  |  | Logic to aggregate data based on profile interest settings. |  |  | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
| 16 | Community Site |  |  | 4 |  | 2 | 32 | 64 | 48 | 3 | [5 empty] | 0 | 0 | 0 | 64 | 0 |  | 0 | 0 | 0 | 32 | 0 |  | 0 | 0 | 0 | 48 | 0
Tim |  | Voting And Flagging | Voting and Flagging |  |  | 3
tim |  | Voting And Flagging | AJAX Jquery |  |  | 3
Brian |  | Voting And Flagging | API end point vote |  |  | 2
Brian |  | Voting And Flagging | API end point flagging |  |  | 2
| 17 | Community Site | Share it functionality(discussion, articles) |  | 2 |  | 2 | 32 | 64 | 48 | 1 |  |  | Add This |  |  | 0 | 64 | 0 | 0 | 0 |  | 0 | 32 | 0 | 0 | 0 |  | 0 | 48 | 0 | 0 | 0
Jason |  | Share It | FED |  |  | 3
Jason |  | Share It | Templetes |  |  | 5
| 18 | Community site | Emails Responsys Integration |  | 3 |  | 5 | 80 | 160 | 120 | 10 |  |  | Integration with responsys |  |  | 0 | 0 | 160 | 0 | 0 |  | 0 | 0 | 80 | 0 | 0 |  | 0 | 0 | 120 | 0 | 0
Dan |  | Responsys | Collect User Data to triggering emails (see user profile) |  |  | 8
Dan |  | Responsys | Cron to send to responsys |  |  | 8
Dan |  | Responsys | Daily Cron |  |  | 8
Sebastian | 19 | Community site | Google analytics |  | 1 | 3 | 1 | 16 | 32 | 24 | 0 | [5 empty] | 16 | 0 | 0 | 0 | 0 |  | 16 | 0 | 0 | 0 | 0 |  | 24 | 0 | 0 | 0 | 0
Sebastian | 20 | Community site | Prafanity filter | spike story talk to pavan. Brendan | 2 | 8 | 2 | 32 | 64 | 48 | 0 | [5 empty] | 0 | 64 | 0 | 0 | 0 |  | 0 | 32 | 0 | 0 | 0 |  | 0 | 48 | 0 | 0 | 0
| 21 | Community site | Interest Page - Customer Service |  | 1 |  | 5 | 80 | 160 | 120 | 0 | [5 empty] | 80 | 0 | 0 | 0 | 0 |  | 80 | 0 | 0 | 0 | 0 |  | 120 | 0 | 0 | 0 | 0
|  | Customer Service Page | See Home |  |  | 8
|  | Customer Service Page | Build None Home Page items |  |  | 8
| 22 | Community site | Interest Page - 2 Category Template Page |  | 1 |  | 3 | 48 | 96 | 72 | 0 | [5 empty] | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
Jason/Tim |  | Interest Page | Template A |  |  | 5
Jason/Tim |  | Interest Page | Template B |  |  | 5
Jason | 23 | Community site | Comments (Blogs, Articles) |  | 1 | 3 | 1 | 16 | 32 | 24 | 6 | [5 empty] | 16 | 0 | 0 | 0 | 0 |  | 16 | 0 | 0 | 0 | 0 |  | 24 | 0 | 0 | 0 | 0
| 24 | Migration | Migrate forums |  | 1 | 16 | 5 | 80 | 160 | 120 | 0 |  |  | View Points provides conversion data |  |  | 80 | 0 | 0 | 0 | 0 |  | 80 | 0 | 0 | 0 | 0 |  | 120 | 0 | 0 | 0 | 0
| 25 | Migration | Migrate articles |  | 2 | 8 | 3 | 48 | 96 | 72 | 0 |  |  | View Points provides conversion data |  |  | 0 | 96 | 0 | 0 | 0 |  | 0 | 48 | 0 | 0 | 0 |  | 0 | 72 | 0 | 0 | 0
| 26 | Migration | Migrate blogs |  | 2 | 8 | 3 | 48 | 96 | 72 | 0 |  |  | View Points provides conversion data |  |  | 0 | 96 | 0 | 0 | 0 |  | 0 | 48 | 0 | 0 | 0 |  | 0 | 72 | 0 | 0 | 0
| 27 | Migration | Migrate User Info |  | 2 | 16 | 5 | 80 | 160 | 120 | 0 |  |  | View Points provides conversion data |  |  | 0 | 160 | 0 | 0 | 0 |  | 0 | 80 | 0 | 0 | 0 |  | 0 | 120 | 0 | 0 | 0
| 28 | Migration | Search index all migrated contents |  | 3 | 16 | 5 | 80 | 160 | 120 | 0 |  |  | View Points provides conversion data |  |  | 0 | 0 | 160 | 0 | 0 |  | 0 | 0 | 80 | 0 | 0 |  | 0 | 0 | 120 | 0 | 0
Jason | 29 | Misc | Setup data & taxonomy | Hamid | 1 | 24 | 8 | 128 | 256 | 192 | 1 |  |  | This is step1 before building any functionality. |  |  | 128 | 0 | 0 | 0 | 0 |  | 128 | 0 | 0 | 0 | 0 |  | 192 | 0 | 0 | 0 | 0
| 30 | Misc | Support old URL's redirects | Follow Up Brendan | 1 |  | 8 | 128 | 256 | 192 | 0 |  |  | Create support for OLD URL's toredirect to the new site URL's |  |  | 128 | 0 | 0 | 0 | 0 |  | 128 | 0 | 0 | 0 | 0 |  | 192 | 0 | 0 | 0 | 0
Sebastian | 31 | Misc | Architecture |  | 3 | 8 | 5 | 80 | 160 | 120 | 0 |  |  | Server setup. Cacheing |  |  | 0 | 0 | 160 | 0 | 0 |  | 0 | 0 | 80 | 0 | 0 |  | 0 | 0 | 120 | 0 | 0
Sebastian | 32 | Misc | Setup environments (Dev,QA,integration,Prod) |  | 1 | 8 | 3 | 48 | 96 | 72 | 0 | [5 empty] | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
Sebastian | 33 | Misc | Performance testing |  | 1 | 8 | 3 | 48 | 96 | 72 | 0 | [5 empty] | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
Sebastian | 34 | Misc | Continous integration environment |  | 1 | 3 | 1 | 16 | 32 | 24 | 0 | [5 empty] | 16 | 0 | 0 | 0 | 0 |  | 16 | 0 | 0 | 0 | 0 |  | 24 | 0 | 0 | 0 | 0
Sebastian | 35 | Misc | Iterative production releases 1 |  | 1 | 3 | 1 | 16 | 32 | 24 | 0 | [5 empty] | 16 | 0 | 0 | 0 | 0 |  | 16 | 0 | 0 | 0 | 0 |  | 24 | 0 | 0 | 0 | 0
Sebastian | 36 | Misc | Iterative production releases 2 |  | 2 | 3 | 1 | 16 | 32 | 24 | 0 | [5 empty] | 0 | 32 | 0 | 0 | 0 |  | 0 | 16 | 0 | 0 | 0 |  | 0 | 24 | 0 | 0 | 0
Sebastian | 37 | Misc | Iterative production releases 3 |  | 3 | 3 | 1 | 16 | 32 | 24 | 0 | [5 empty] | 0 | 0 | 32 | 0 | 0 |  | 0 | 0 | 16 | 0 | 0 |  | 0 | 0 | 24 | 0 | 0
Sebastian | 38 | Misc | Iterative production releases 4 |  | 4 | 3 | 1 | 16 | 32 | 24 | 0 | [5 empty] | 0 | 0 | 0 | 32 | 0 |  | 0 | 0 | 0 | 16 | 0 |  | 0 | 0 | 0 | 24 | 0
Sebastian | 39 | Misc | Iterative production releases 5 |  | 5 | 3 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| 40 | Misc | Meetings Iteration 1 |  | 1 | 8 | 2 | 32 | 64 | 48 | 0 | [5 empty] | 32 | 0 | 0 | 0 | 0 |  | 32 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0
| 41 | Misc | Meetings Iteration 2 |  | 2 | 8 | 2 | 32 | 64 | 48 | 0 | [5 empty] | 0 | 64 | 0 | 0 | 0 |  | 0 | 32 | 0 | 0 | 0 |  | 0 | 48 | 0 | 0 | 0
| 42 | Misc | Meetings Iteration 3 |  | 3 | 8 | 2 | 32 | 64 | 48 | 0 | [5 empty] | 0 | 0 | 64 | 0 | 0 |  | 0 | 0 | 32 | 0 | 0 |  | 0 | 0 | 48 | 0 | 0
| 43 | Misc | Meetings Iteration 4 |  | 4 | 8 | 2 | 32 | 64 | 48 | 0 | [5 empty] | 0 | 0 | 0 | 64 | 0 |  | 0 | 0 | 0 | 32 | 0 |  | 0 | 0 | 0 | 48 | 0
| 44 | Misc | Meetings Iteration 5 |  | 5 | 8 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| 45 | Admin/moderation | Display flagged content & delete inappropriate entries(coments, questions) |  | 1 | 8 | 3 | 48 | 96 | 72 | 6 | [5 empty] | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
| 46 | Admin/moderation | Ldap login |  | 1 |  | 1 | 16 | 32 | 24 | 6 | [5 empty] | 16 | 0 | 0 | 0 | 0 |  | 16 | 0 | 0 | 0 | 0 |  | 24 | 0 | 0 | 0 | 0
Sebastian |  | LDAP Login | Talks to Meeks |  |  | 3
Jason |  | LDAP Login | FED Work (update WP-Admin |  |  | 3
| 47 | Admin/moderation | Reporting |  | 4 | 8 | 2 | 32 | 64 | 48 | 6 | [5 empty] | 0 | 0 | 0 | 64 | 0 |  | 0 | 0 | 0 | 32 | 0 |  | 0 | 0 | 0 | 48 | 0
| 48 | Home Page | Home page content mgmt. |  | 1 | 8 | 3 | 48 | 96 | 72 | 6 |  |  | Hero Image, Featured Article - (FA Lite) |  |  | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
| 49 | CMS | Author buying guides | Any sort of admin work | 1 | 3 | 1 | 16 | 32 | 24 | 6 | [5 empty] | 16 | 0 | 0 | 0 | 0 |  | 16 | 0 | 0 | 0 | 0 |  | 24 | 0 | 0 | 0 | 0
| 50 | CMS | Author blogs | Any sort of admin work | 1 | 8 | 3 | 48 | 96 | 72 | 6 | [5 empty] | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
| 51 | CMS | Experts Q & A | Any sort of admin work | 1 | 24 | 8 | 128 | 256 | 192 | 6 | [5 empty] | 128 | 0 | 0 | 0 | 0 |  | 128 | 0 | 0 | 0 | 0 |  | 192 | 0 | 0 | 0 | 0
| 52 | Feeds | Syndication | ?? | 3 |  | 3 | 48 | 96 | 72 | 0 | [5 empty] | 0 | 0 | 96 | 0 | 0 |  | 0 | 0 | 48 | 0 | 0 |  | 0 | 0 | 72 | 0 | 0
| 53 | Resource | FED Iteration 1 |  | 1 |  | 40 | 640 | 1280 | 960 | 0 | [5 empty] | 640 | 0 | 0 | 0 | 0 |  | 640 | 0 | 0 | 0 | 0 |  | 960 | 0 | 0 | 0 | 0
| 54 | Resource | FED Iteration 2 |  | 2 |  | 15 | 240 | 480 | 360 | 0 | [5 empty] | 0 | 480 | 0 | 0 | 0 |  | 0 | 240 | 0 | 0 | 0 |  | 0 | 360 | 0 | 0 | 0
| 55 | Resource | FED Iteration 3 |  | 3 |  | 5 | 80 | 160 | 120 | 0 | [5 empty] | 0 | 0 | 160 | 0 | 0 |  | 0 | 0 | 80 | 0 | 0 |  | 0 | 0 | 120 | 0 | 0
| 56 | Resource | FED Iteration 4 |  | 4 |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| 57 | Resource | FED Iteration 5 |  | 5 |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| 58 | Community Site | Manuals | 200 hours | 5 |  | 8 | 128 | 256 | 192 | 0
| 59 | Community Site | Following |  | 2 | 8 | 2 | 32 | 64 | 48 | 0
| 60 | Community Site | Polls |  | 4 | 13 | 3 | 48 | 96 | 72 | 0
[17 empty] | Low | High | High | High | High |  | Low | Low | Low | Low | Low |  | Avg | Avg | Avg | Avg | Avg
[5 empty] | Totals |  | 247 | 4080 | 7648 | 5800 | [5 empty] | Total Hours | 2464 | 1056 | 864 | 384 | 256 |  | 2464 | 528 | 432 | 192 | 128 |  | 3568 | 792 | 648 | 288 | 192
[16 empty] | Weeks | 68.4444 | 29.3333 | 24 | 10.6667 | 7.1111 |  | 68.4444 | 14.6667 | 12 | 5.3333 | 3.5556 |  | 99.1111 | 22 | 18 | 8 | 5.3333
[16 empty] | Actual Weeks | 12 | 3 | 3 | 3 | 3 |  | 12 | 3 | 3 | 3 | 3 |  | 12 | 3 | 3 | 3 | 3
[16 empty] | # of Dev | 5.7037 | 9.7778 | 8 | 3.5556 | 2.3704 |  | 5.7037 | 4.8889 | 4 | 1.7778 | 1.1852 |  | 8.2593 | 7.3333 | 6 | 2.6667 | 1.7778
[16 empty] | Grand Total Hours |  |  |  |  | 5024 | [6 empty] | 3744 |  |  |  |  | 5488
[16 empty] | Iteration 1 | low | 2464 |  |  |  | 2464
[16 empty] | Iteration 2-4 | avg | 1920 |  |  |  | 1600
[16 empty] | QA |  | 1480 |  |  |  | 1300
[16 empty] | BA |  | 600 |  |  |  | 600
[16 empty] | Training |  | 160 | iteration 4 -5 |  |  | 160
[16 empty] | Total |  | 6464 |  | 55 | 355520 | 6124
Note on A16: The category to which this story belongs, if any.
Note on B16: The category to which this story belongs, if any.
Note on C16: The category to which this story belongs, if any.
Note on F16: If known, the Track that will deliver this story.
Note on H16: The Tech Story Points associated with this story. This value is translated into ABP/HP through velocity.

## Users
Types of user roles | WP-Admin | Admin | Moderator | External User | Expert | Blogger
Edit Content | x | x | x
Ad management | x | x | x
Image and video management | x | x | x | x | x | x
Delete image and video | x | x | x
Blogs and Buying Guides | x |  | x |  |  | x
Profanity filters | x
Blog Comments | x |  | x |  |  | x
Q&A Moderation | x |  | x
Flagged for concern content | x |  | x
Add user | x
Remove/modify user permissions | x
member information (external user) | x |  | x
Assign Badges | x |  | x
Questions from Queue | x |  | x |  | x | x
Ask question | x |  | x | x | x | x
Vote | x |  | x | x | x | x
Answer Question | x |  | x | x | x | x
Follow CAT/question/tag | x |  | x | x | x | x

## Priority
2012-08-29 | 1
Home Page
Search
Login
Profile
Q&A
Interest Page
Mod Tool
CMS
Customer Service
2012-09-12 | 2
Following
Social Share
Expert
Email
2012-09-26 | 3
Enhancing CMS | ?
Refactoring | ?
2012-10-10 | 4
Commenting outside of Q&A
Related Top Rated Products
Enhancing Q&A | ?
Enhancing CMS | ?
2012-10-24 | 5
Enhancing Mod Tool | ?
Ad Units

## UX Estimates
Feature | UX Hours | Copy Hours | Creative Hours | FED Hours | Total Hours per feature
Q&A (3.5, 3.6) | 140 | 16 | 130 | 55.5 | 341.5
Search (3.3) | 200 | 10 | 120 | 57.5 | 387.5
Homepage (3.3, 3.4. 3.12) (Needs to go to Design Review) | 330 | 48 | 310 | 120 | 808
Blog (3.10) | 80 | 8 | 90 | 20 | 198
Interest Page (3.9, 3.10, 3.11) | 200 | 24 | 220 | 45 | 489
Login/Registration (3.1, 3.2) | 60 | 24 | 132 | 80 | 296
Profile (3.1, 3.2, 3.3, 3.7 (logged in state), 3.13, 3.17) | 180 | 76 | 582 | 252.5 | 1090.5
Admin & MOD Tool (?) | 464 |  |  | 359 | 823
Total | 1654 | 206 | 1584 | 989.5 | 4433.5 | 3444 | 86 | 296184

## Risks
Item | Risk | Dependency
1 | Tight deadline because of View Points Contract | View Points
2 | Migration | View Points
3 | Late UX handoffs | UX
4 | Communities mysears.com/mykmart.com dependency. This could become big
5 | Sears Single Sign-On (SSO) | ENG
6 | LDAP | ENG

## Assumptions
Item | Assumption
1 | Migration off of view points is the overall strategic plan
2 | Question and Answers it the most important business objective
3 | Migration: Prerequisite: provide mapping of viewpoints category to new community platform categories/taxonomy. Low - them create a file dump via WXR, Medium - some exporter, High - custom batch. multiple files
4 | Design is satisfactory to the team.
5 | Code is reviewed.
6 | Unit tests coverage is 80% or more.
7 | Story acceptance criteria is met.
8 | No p1 and p2 open jira's.
9 | QA/BA accepted/passed the story.

## Team Sizing
Beta
| DRAFT | [9 empty] | Launch
Project Start | 2012-05-21
Project End | 2012-10-24
[13 empty] | 1 |  |  | 2 |  |  | 3 |  |  | 4 |  |  | 5
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | Total FTE
Location | Track | 2012-05-21 | 2012-05-28 | 2012-06-04 | 2012-06-11 | 2012-06-18 | 2012-06-25 | 2012-07-02 | 2012-07-09 | 2012-07-16 | 2012-07-23 | 2012-07-30 | 2012-08-06 | 2012-08-13 | 2012-08-20 | 2012-08-27 | 2012-09-03 | 2012-09-10 | 2012-09-17 | 2012-09-24 | 2012-10-01 | 2012-10-08 | 2012-10-15 | 2012-10-22 | 2012-10-29 | 2012-11-05 | 2012-11-12 | 2012-11-19 | 2012-11-26 | Staffing
Oversight Roles
0
| Tech Lead | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 140
| Tech Lead | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 140
| Architect | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 32
172
Total Oversight Person Hours |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 0 | 22 | 0 | 22 | 268
Team Roles
| Engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 520
| Eng, Web Developer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 30 | 30 | 30 | 30 | 180
| Eng, QA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 30 | 30 | 30 | 30 | 180
| Business Analyst | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
Total Team Person Hours |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 60 | 60 | 60 | 60 | 360
Grand Total Person Hours |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 82 | 82 | 60 | 82 | 60 | 82 | 628
352000
Roles | Skills | 2012-05-21: Exp. Yrs; 2012-05-28: Nbr; 2012-06-04: Onsite/Offshore
Project/technical lead | Agile development, Status reporting, Team management, Web development, Java, MySQL | 2012-05-21: 8; 2012-05-28: 1; 2012-06-04: SHI
Sr. Developer | Java 1.5, Web development, Spring, Spring MVC, MySQL, JPA/Hibernate/JDBC, Agile development | 2012-05-21: 8; 2012-05-28: 4; 2012-06-04: Onsite
Architect | Java 1.5, Web development, Spring, Spring MVC, MySQL, JPA/Hibernate/JDBC | 2012-05-21: 8; 2012-05-28: 1; 2012-06-04: SHI
Developer | Java 1.5, Web development, Spring, Spring MVC, MySQL, JPA/Hibernate.JDBC | 2012-05-21: 5'; 2012-05-28: 8; 2012-06-04: SHI
Sr QA |  | 2012-05-28: 2; 2012-06-04: Onsite
QA | Manual testing, JIRA | 2012-05-28: 2; 2012-06-04: SHI
Automation QA | Silenium or any other automation tool | 2012-05-28: 1; 2012-06-04: SHI
T Business Analyst |  | 2012-05-28: 1; 2012-06-04: Onsite
Note on A10: Enter all oversight roles with associated percentage allocation (0-1) for each week of the project.

## Release Dates
DRAFT
Iteration Plan
Iteration | Start | Weeks | End | Size | Status | Release Date | Goal | Release
1 | 2012-05-21 | 11 | 2012-08-06 |  | Home Page, Basic Search, Login, Profile, Q&A, Moderation Tool, Blog/Buy Guide, Customer Service Page, Social Share, Experts & Badging, Comments, Google Analytics, Cont. Training | Iteration 1 | 12
2 | 2012-08-06 | 3 | 2012-08-27 |  | Migration, Following, Omniture | Iteration 2 | 3
3 | 2012-08-27 | 3 | 2012-09-17 |  | Enhance CMS, Category Page Templates, Email Notificaitons | Iteration 3 | 3
4 | 2012-09-17 | 3 | 2012-10-08 |  | Polls, Add Units, Voting/Flagging, Reporting | Iteration 4 | 3
5 | 2012-10-08 | 3 | 2012-10-29 |  | Smart Search (Site Search Auto-Complete), Manuals, JS Widget, QA | Iteration 5 | 3