## Summary
Iteration | 1 | 2 | 3 | 4 | 5
Launch Date | 2012-08-06 | 2012-08-27 | 2012-09-17 | 2012-10-08 | 2012-10-29
Eng Estimate
FED Estimate
Total Estimate

## Estimate
Estimated 1 Point
Low | 16
High | 32
Total Points | 236
Low | 3776
High | 7552
Average | 5664
Our Points |  | Estimated Points
Point | Hours | Points | Hours
1 | 4 | 1 | 16
2 | 8 | 2 | 32
3 | 16 | 3 | 48
5 | 30 | 4 | 64
8 | 40 | 5 | 80 | [8 empty] | average | 3120 | #REF! |  |  | 12 weeks | 4 weeks
Track Total Hours
LOE in Hours Calculated
| Req # | Story # | Epic | User Story |  | Iteration | Our Points | Points | Low | High | Average | UX Priority | Eng Priority | Dependency | Notes |  | Low | High | High | High | High |  | Low | Low | Low | Low | Low |  | Avg | Avg | Avg | Avg | Avg
[5 empty] | Possible solution | [11 empty] | 1 | 2 | 3 | 4 | 5 |  | 1 | 2 | 3 | 4 | 5 |  | 1 | 2 | 3 | 4 | 5
|  | 1 | Community Site | Home page - Logged in/Logged out(Hero image, articles, QA activity, Twitter feed, total members) |  | 1 | 0 | 8 | 128 | 256 | 192 | 1 |  |  |  |  | 128 | 0 | 0 | 0 | 0 |  | 128 | 0 | 0 | 0 | 0 |  | 192 | 0 | 0 | 0 | 0
|  | 1.1 | Community Site | Community Header |  | 1 | 3
|  | 1.2 | Community Site | Community Global Navigation | WP Menus | 1 | 3 |  | 128
|  | 100 | Home Page | See all Experts (we are here to help) | http://blog.fitstudio.com/ - Blog Contributors | 1 | 3
|  | 100.1 | Home Page | Featured Blog | FA Lite - plugin | 1 | 3
|  | 100.2 | Home Page | Ask A Question | custom | 1 | 5
|  | 100.3 | Home Page | Featured Q&A | Widget by categories | 1 | 3
|  | 100.4 | Home Page | Poll of the week | Iteration 4 | 1 | 0
|  | 100.5 | Home Page | Add Unit | CQ5, iteration 4 | 1 | 0
|  | 100.6 | Home Page | Recent Activity | by asking, answering and following content | 1 | 3
|  | 1.3 | Community Site | Community Footer |  | 1 | 3
| Tim | 100.7 | Home Page | FED |  | 1 | 40 | 12 | 192 | 384 | 288 | 2 |  |  |  |  | 192 | 0 | 0 | 0 | 0 |  | 192 | 0 | 0 | 0 | 0 |  | 288 | 0 | 0 | 0 | 0
|  | 2 | Community Site | Q & A (discussions) |  | 1 | 0 | 8 | 128 | 0 | 64 | 2 |  |  | (CPT) Custom Post Type post_type=question as a parent parent_post=0. (CPT) post_type=answer, parent_post={questionID} |  | 128 | 0 | 0 | 0 | 0 |  | 128 | 0 | 0 | 0 | 0 |  | 64 | 0 | 0 | 0 | 0
| Eddie | 2.1 | Q And A | Architect | wp_posts.post_type index field for searching | 1 | 2
|  | 2.2 | Q And A | Question = Post | SSO users are asking questions | 1 | 3
|  | 2.2 | Q And A | Comment = Answer | Nesting comments | 1 | 3
| Tim | 2.2 | Q And A | FED |  | 1 | 11 | 4 | 64 | 128 | 96 | 2
|  | 3 | Community Site | Blog |  | 1 | 0 | 3 | 48 | 96 | 72 | 1 |  |  | templates = single, archive, aside for video |  | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
|  | 3.1 | Blog | 404 |  | 1 | 3
|  | 3.2 | Blog | Archvie | Includes, tags, category, search results | 1 | 3
|  | 3.3 | Blog | Single |  | 1 | 3
|  | 3.4 | Blog | Page | This goes to interest and customer service | 1 | 0
|  | 3.5 | Blog | FED |  | 1 | 48 | 10 | 160 | 320 | 240 | 1
|  | 4 | User Profile | User profile page (My discussions, photo, Interests, badges) |  | 1 | 0 | 5 | 80 | 160 | 120 | 2 |  |  |  |  | 80 | 0 | 0 | 0 | 0 |  | 80 | 0 | 0 | 0 | 0 |  | 120 | 0 | 0 | 0 | 0
| Jason | 4.1 | User Profile | Dashboard |  | 1 | 5
| Jason | 4.2 | User Profile | My Discussions & Answers |  | 1 | 3
| Jason | 4.3 | User Profile | My Following |  | 1 | 3
| Jason | 4.4 | User Profile | Change My Setting | Unfollow and stopping emails | 1 | 2
| Jason | 4.5 | User Profile | My Votes |  | 1 | 2
| Jason | 4.6 | User Profile | My Flags |  | 1 | 2
|  | 4.7 | User Profile | FED |  | 1 | 48 | 16 | 256 | 512 | 384 | 2
|  | 5 | Community Site | User Admin Settings Page |  | 1 | 8 | 3 | 48 | 96 | 72 | 4 |  |  | Place where they can turn off (opt-out) of following |  | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
|  | 6 | Community Site | Articles (Guides) |  | 1 | 3 | 2 | 32 | 64 | 48 | 3 |  |  |  |  | 32 | 0 | 0 | 0 | 0 |  | 32 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0
|  | 7 | Community Site | Ad units on pages |  | 4 | 16 | 5 | 80 | 160 | 120 | 0 |  |  | Use CQ5 |  | 0 | 0 | 0 | 160 | 0 |  | 0 | 0 | 0 | 80 | 0 |  | 0 | 0 | 0 | 120 | 0
|  | 8 | Community Site | Site search (discussions, articles, blogs) |  | 1 | 8 | 3 | 48 | 96 | 72 | 3 |  |  | Indexing of blog and store pages is new addition. |  | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
|  | 9 | Search | Site Search - Auto Complete |  | 5 |  | 8 | 128 | 256 | 192 | 0 |  |  | will require mongo DB |  | 0 | 0 | 0 | 0 | 256 |  | 0 | 0 | 0 | 0 | 128 |  | 0 | 0 | 0 | 0 | 192
|  | 9.1 | Search | Mongo DB setup |  |  | 8
|  | 9.2 | Search | Code Integration |  |  | 8
|  | 9.3 | Search | Jquery |  |  | 8
|  | 9.4 | Search | Stress testing |  |  | 3
|  | 9.5 | Search | FED |  |  |  | 4 | 64 | 128 | 96 | 0
| Brian/Dan | 10 | Community Site | SSO |  | 1 | 0 | 5 | 80 | 160 | 120 | 0 |  |  | Profile/SSO will take care of validating and authenticating open id just like user/password |  | 80 | 0 | 0 | 0 | 0 |  | 80 | 0 | 0 | 0 | 0 |  | 120 | 0 | 0 | 0 | 0
| Brian/Dan | 10.1 | Login | SSO |  |  | 8
| Brian/Dan | 10.2 | Login | Open ID - Facebook |  |  | 8
| Brian/Dan | 10.3 | Login | Create Login |  |  | 5
| Brian/Dan | 10.4 | Login | Integration / Security |  |  | 3
| Brian/Dan | 11 | Community Site |  |  | 1 |  | 5 | 80 | 160 | 120 | 2 |  |  |  |  | 80 | 0 | 0 | 0 | 0 |  | 80 | 0 | 0 | 0 | 0 |  | 120 | 0 | 0 | 0 | 0
| Brian/Dan |  | Login | User Login |  |  | 2
| Brian/Dan |  | Login | Login/ Logout |  |  | 2
| Brian/Dan |  | Login | FED |  | 1 | 40 | 12 | 192 | 384 | 288 | 2
| Sebastian | 12 | Community Site | Feedback (Qualtrics) |  | 3 | 5 | 1 | 16 | 32 | 24 | 0 |  |  |  |  | 0 | 0 | 32 | 0 | 0 |  | 0 | 0 | 16 | 0 | 0 |  | 0 | 0 | 24 | 0 | 0
| Tim/Jason | 13 | Community Site | Contacts page |  | 1 | 3 | 1 | 16 | 32 | 24 | 5 |  |  |  |  | 16 | 0 | 0 | 0 | 0 |  | 16 | 0 | 0 | 0 | 0 |  | 24 | 0 | 0 | 0 | 0
|  | 14 | Community Site | Tag/filter content |  | 1 |  | 8 | 128 | 256 | 192 | 2 |  |  | Separate installation for each site. Double UX work |  | 128 | 0 | 0 | 0 | 0 |  | 128 | 0 | 0 | 0 | 0 |  | 192 | 0 | 0 | 0 | 0
|  | 15 | User Profile | Activity feed based on profile |  | 1 | 8 | 3 | 48 | 96 | 72 | 0 |  |  | Logic to aggregate data based on profile interest settings. |  | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
|  | 16 | Community Site | Voting and Flagging |  | 4 | 0 | 2 | 32 | 64 | 48 | 3 |  |  |  |  | 0 | 0 | 0 | 64 | 0 |  | 0 | 0 | 0 | 32 | 0 |  | 0 | 0 | 0 | 48 | 0
| Tim | 16.1 | Voting And Flagging | Voting and Flagging |  |  | 3
| tim | 16.2 | Voting And Flagging | AJAX Jquery |  |  | 3
| Brian | 16.3 | Voting And Flagging | API end point vote |  |  | 2
| Brian | 16.4 | Voting And Flagging | API end point flagging |  |  | 2
|  | 17 | Community Site | Share it functionality(discussion, articles) |  | 2 | 0 | 2 | 32 | 64 | 48 | 1 |  |  | Add This |  | 0 | 64 | 0 | 0 | 0 |  | 0 | 32 | 0 | 0 | 0 |  | 0 | 48 | 0 | 0 | 0
| Jason | 17.1 | Share It | FED |  |  | 3
| Jason | 17.2 | Share It | Templetes |  |  | 5
|  | 18 | Community site | Emails Responsys Integration |  | 3 | 0 | 5 | 80 | 160 | 120 | 10 |  |  | Integration with responsys |  | 0 | 0 | 160 | 0 | 0 |  | 0 | 0 | 80 | 0 | 0 |  | 0 | 0 | 120 | 0 | 0
| Dan | 18.1 | Responsys | Collect User Data to triggering emails (see user profile) |  |  | 8
| Dan | 18.2 | Responsys | Cron to send to responsys |  |  | 8
| Dan | 18.3 | Responsys | Daily Cron |  |  | 8
| Sebastian | 19 | Community site | Google analytics |  | 1 | 3 | 1 | 16 | 32 | 24 | 0 |  |  |  |  | 16 | 0 | 0 | 0 | 0 |  | 16 | 0 | 0 | 0 | 0 |  | 24 | 0 | 0 | 0 | 0
| Sebastian | 20 | Community site | Prafanity filter | spike story talk to pavan. Brendan | 2 | 8 | 2 | 32 | 64 | 48 | 0 |  |  |  |  | 0 | 64 | 0 | 0 | 0 |  | 0 | 32 | 0 | 0 | 0 |  | 0 | 48 | 0 | 0 | 0
|  | 21 | Community site | Interest Page - Customer Service |  | 1 |  | 5 | 80 | 160 | 120 | 0 |  |  |  |  | 80 | 0 | 0 | 0 | 0 |  | 80 | 0 | 0 | 0 | 0 |  | 120 | 0 | 0 | 0 | 0
|  |  | Customer Service Page | See Home |  |  | 8
|  |  | Customer Service Page | Build None Home Page items |  |  | 8
|  | 22 | Community site | Interest Page - 2 Category Template Page |  | 1 |  | 3 | 48 | 96 | 72 | 0 |  |  |  |  | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
| Jason/Tim |  | Interest Page | Template A |  |  | 5
| Jason/Tim |  | Interest Page | Template B |  |  | 5
|  |  | Interest Page | FED |  |  |  | 4 | 64 | 128 | 96 | 0
| Jason | 23 | Community site | Comments (Blogs, Articles) |  | 1 | 3 | 1 | 16 | 32 | 24 | 6 |  |  |  |  | 16 | 0 | 0 | 0 | 0 |  | 16 | 0 | 0 | 0 | 0 |  | 24 | 0 | 0 | 0 | 0
|  | 24 | Migration | Migrate forums |  | 1 | 16 | 5 | 80 | 160 | 120 | 0 |  |  | View Points provides conversion data |  | 80 | 0 | 0 | 0 | 0 |  | 80 | 0 | 0 | 0 | 0 |  | 120 | 0 | 0 | 0 | 0
|  | 25 | Migration | Migrate articles |  | 2 | 8 | 3 | 48 | 96 | 72 | 0 |  |  | View Points provides conversion data |  | 0 | 96 | 0 | 0 | 0 |  | 0 | 48 | 0 | 0 | 0 |  | 0 | 72 | 0 | 0 | 0
|  | 26 | Migration | Migrate blogs |  | 2 | 8 | 3 | 48 | 96 | 72 | 0 |  |  | View Points provides conversion data |  | 0 | 96 | 0 | 0 | 0 |  | 0 | 48 | 0 | 0 | 0 |  | 0 | 72 | 0 | 0 | 0
|  | 27 | Migration | Migrate User Info |  | 2 | 16 | 5 | 80 | 160 | 120 | 0 |  |  | View Points provides conversion data |  | 0 | 160 | 0 | 0 | 0 |  | 0 | 80 | 0 | 0 | 0 |  | 0 | 120 | 0 | 0 | 0
|  | 28 | Migration | Search index all migrated contents |  | 3 | 16 | 5 | 80 | 160 | 120 | 0 |  |  | View Points provides conversion data |  | 0 | 0 | 160 | 0 | 0 |  | 0 | 0 | 80 | 0 | 0 |  | 0 | 0 | 120 | 0 | 0
| Jason | 29 | Misc | Setup data & taxonomy | Hamid | 1 | 24 | 8 | 128 | 256 | 192 | 1 |  |  | This is step1 before building any functionality. |  | 128 | 0 | 0 | 0 | 0 |  | 128 | 0 | 0 | 0 | 0 |  | 192 | 0 | 0 | 0 | 0
|  | 30 | Misc | Support old URL's redirects | Follow Up Brendan | 1 |  | 8 | 128 | 256 | 192 | 0 |  |  | Create support for OLD URL's toredirect to the new site URL's |  | 128 | 0 | 0 | 0 | 0 |  | 128 | 0 | 0 | 0 | 0 |  | 192 | 0 | 0 | 0 | 0
| Sebastian | 31 | Misc | Architecture |  | 3 | 8 | 5 | 80 | 160 | 120 | 0 |  |  | Server setup. Cacheing |  | 0 | 0 | 160 | 0 | 0 |  | 0 | 0 | 80 | 0 | 0 |  | 0 | 0 | 120 | 0 | 0
| Sebastian | 32 | Misc | Setup environments (Dev,QA,integration,Prod) |  | 1 | 8 | 3 | 48 | 96 | 72 | 0 |  |  |  |  | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
| Sebastian | 33 | Misc | Performance testing |  | 1 | 8 | 3 | 48 | 96 | 72 | 0 |  |  |  |  | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
| Sebastian | 34 | Misc | Continous integration environment |  | 1 | 3 | 1 | 16 | 32 | 24 | 0 |  |  |  |  | 16 | 0 | 0 | 0 | 0 |  | 16 | 0 | 0 | 0 | 0 |  | 24 | 0 | 0 | 0 | 0
| Sebastian | 35 | Misc | Iterative production releases 1 |  | 1 | 3 | 1 | 16 | 32 | 24 | 0 |  |  |  |  | 16 | 0 | 0 | 0 | 0 |  | 16 | 0 | 0 | 0 | 0 |  | 24 | 0 | 0 | 0 | 0
| Sebastian | 36 | Misc | Iterative production releases 2 |  | 2 | 3 | 1 | 16 | 32 | 24 | 0 |  |  |  |  | 0 | 32 | 0 | 0 | 0 |  | 0 | 16 | 0 | 0 | 0 |  | 0 | 24 | 0 | 0 | 0
| Sebastian | 37 | Misc | Iterative production releases 3 |  | 3 | 3 | 1 | 16 | 32 | 24 | 0 |  |  |  |  | 0 | 0 | 32 | 0 | 0 |  | 0 | 0 | 16 | 0 | 0 |  | 0 | 0 | 24 | 0 | 0
| Sebastian | 38 | Misc | Iterative production releases 4 |  | 4 | 3 | 1 | 16 | 32 | 24 | 0 |  |  |  |  | 0 | 0 | 0 | 32 | 0 |  | 0 | 0 | 0 | 16 | 0 |  | 0 | 0 | 0 | 24 | 0
| Sebastian | 39 | Misc | Iterative production releases 5 |  | 5 | 3 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 40 | Misc | Meetings Iteration 1 |  | 1 | 8 | 2 | 32 | 64 | 48 | 0 |  |  |  |  | 32 | 0 | 0 | 0 | 0 |  | 32 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0
|  | 41 | Misc | Meetings Iteration 2 |  | 2 | 8 | 2 | 32 | 64 | 48 | 0 |  |  |  |  | 0 | 64 | 0 | 0 | 0 |  | 0 | 32 | 0 | 0 | 0 |  | 0 | 48 | 0 | 0 | 0
|  | 42 | Misc | Meetings Iteration 3 |  | 3 | 8 | 2 | 32 | 64 | 48 | 0 |  |  |  |  | 0 | 0 | 64 | 0 | 0 |  | 0 | 0 | 32 | 0 | 0 |  | 0 | 0 | 48 | 0 | 0
|  | 43 | Misc | Meetings Iteration 4 |  | 4 | 8 | 2 | 32 | 64 | 48 | 0 |  |  |  |  | 0 | 0 | 0 | 64 | 0 |  | 0 | 0 | 0 | 32 | 0 |  | 0 | 0 | 0 | 48 | 0
|  | 44 | Misc | Meetings Iteration 5 |  | 5 | 8 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 45 | Admin/moderation | Display flagged content & delete inappropriate entries(coments, questions) |  | 1 | 8 | 3 | 48 | 96 | 72 | 6 |  |  |  |  | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
|  | 46 | Admin/moderation | Ldap login |  | 1 |  | 1 | 16 | 32 | 24 | 6 |  |  |  |  | 16 | 0 | 0 | 0 | 0 |  | 16 | 0 | 0 | 0 | 0 |  | 24 | 0 | 0 | 0 | 0
| Sebastian |  | LDAP Login | Talks to Meeks |  |  | 3
| Jason |  | LDAP Login | FED Work (update WP-Admin |  |  | 3
|  | 47 | Admin/moderation | Reporting |  | 4 | 8 | 2 | 32 | 64 | 48 | 6 |  |  |  |  | 0 | 0 | 0 | 64 | 0 |  | 0 | 0 | 0 | 32 | 0 |  | 0 | 0 | 0 | 48 | 0
|  | 48 | Home Page | Home page content mgmt. |  | 1 | 8 | 3 | 48 | 96 | 72 | 6 |  |  | Hero Image, Featured Article - (FA Lite) |  | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
|  | 49 | CMS | Author buying guides | Any sort of admin work | 1 | 3 | 1 | 16 | 32 | 24 | 6 |  |  |  |  | 16 | 0 | 0 | 0 | 0 |  | 16 | 0 | 0 | 0 | 0 |  | 24 | 0 | 0 | 0 | 0
|  | 50 | CMS | Author blogs | Any sort of admin work | 1 | 8 | 3 | 48 | 96 | 72 | 6 |  |  |  |  | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
|  | 51 | CMS | Experts Q & A | Any sort of admin work | 1 | 24 | 8 | 128 | 256 | 192 | 6 |  |  |  |  | 128 | 0 | 0 | 0 | 0 |  | 128 | 0 | 0 | 0 | 0 |  | 192 | 0 | 0 | 0 | 0
|  | 52 | Feeds | Syndication | ?? | 3 |  | 3 | 48 | 96 | 72 | 0 |  |  |  |  | 0 | 0 | 96 | 0 | 0 |  | 0 | 0 | 48 | 0 | 0 |  | 0 | 0 | 72 | 0 | 0
|  | 53 | Resource | FED Iteration 1 |  | 1 |  | 40 | 640 | 1280 | 960 | 0 |  |  |  |  | 640 | 0 | 0 | 0 | 0 |  | 640 | 0 | 0 | 0 | 0 |  | 960 | 0 | 0 | 0 | 0
|  | 54 | Resource | FED Iteration 2 |  | 2 |  | 15 | 240 | 480 | 360 | 0 |  |  |  |  | 0 | 480 | 0 | 0 | 0 |  | 0 | 240 | 0 | 0 | 0 |  | 0 | 360 | 0 | 0 | 0
|  | 55 | Resource | FED Iteration 3 |  | 3 |  | 5 | 80 | 160 | 120 | 0 |  |  |  |  | 0 | 0 | 160 | 0 | 0 |  | 0 | 0 | 80 | 0 | 0 |  | 0 | 0 | 120 | 0 | 0
|  | 56 | Resource | FED Iteration 4 |  | 4 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 57 | Resource | FED Iteration 5 |  | 5 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 58 | Community Site | Manuals | 200 hours | 5 |  | 8 | 128 | 256 | 192 | 0
|  | 59 | Community Site | Following |  | 2 | 8 | 2 | 32 | 64 | 48 | 0
|  | 60 | Community Site | Polls |  | 4 | 13 | 3 | 48 | 96 | 72 | 0
[17 empty] | Low | High | High | High | High |  | Low | Low | Low | Low | Low |  | Avg | Avg | Avg | Avg | Avg
[6 empty] | Totals |  | 309 | 5072 | 9632 | 7288 |  |  |  |  | Total Hours | 2656 | 1056 | 864 | 384 | 256 |  | 2656 | 528 | 432 | 192 | 128 |  | 3856 | 792 | 648 | 288 | 192
[16 empty] | Weeks | 73.7778 | 29.3333 | 24 | 10.6667 | 7.1111 |  | 73.7778 | 14.6667 | 12 | 5.3333 | 3.5556 |  | 107.1111 | 22 | 18 | 8 | 5.3333
[16 empty] | Actual Weeks | 12 | 3 | 3 | 3 | 3 |  | 12 | 3 | 3 | 3 | 3 |  | 12 | 3 | 3 | 3 | 3
[16 empty] | # of Dev | 6.1481 | 9.7778 | 8 | 3.5556 | 2.3704 |  | 6.1481 | 4.8889 | 4 | 1.7778 | 1.1852 |  | 8.9259 | 7.3333 | 6 | 2.6667 | 1.7778
[16 empty] | Grand Total Hours |  |  |  |  | 5216 | [6 empty] | 3936 |  |  |  |  | 5776
[16 empty] | Iteration 1 | low | 2656 |  |  |  | 2656
[16 empty] | Iteration 2-4 | avg | 1920 |  |  |  | 1600
[16 empty] | QA |  | 1520 |  |  |  | 1300
[16 empty] | BA |  | 600 |  |  |  | 600
[16 empty] | Training |  | 160 | iteration 4 -5 |  |  | 160
[16 empty] | Total |  | 6696 |  | 55 | 368280 | 6316
Note on B20: The category to which this story belongs, if any.
Note on C20: The category to which this story belongs, if any.
Note on D20: The category to which this story belongs, if any.
Note on G20: If known, the Track that will deliver this story.
Note on I20: The Tech Story Points associated with this story. This value is translated into ABP/HP through velocity.

## Users
Req. # | Features | WP-Admin | Admin | Moderator | External User | Expert | Blogger
3.3 | CMS
3.3.1 | Homepage
| • Assign Admin rights • Inputs text for Promo in Nav bar • Add/remove content from or to each module |  | x | x
3.3.2 | Ad Management
| • Upload Ad Units • Designate Ad Unit Location • Remove Ad Units • Schedule Ad Units |  | x | x
3.3.3 | Image & Video Management
| • Store images & Videos to centralized location to upload to Blogs and etc. • Add or delete image and video tags • Email images from tool |  | x | x |  |  | x
| • Delete images and videos |  | x | x
3.3.4 | Blogs and Buying Guides
| • Preview, Draft, Cancel |  | x | x |  | x | x
| • Schedule and Publish |  | x
3.3.5 | Category Pages
| • Add, delete,and modify |  | x | x
3.4 | Moderation
3.4.1 | Profanity Filters |  | x
3.4.2 | Blog Comments |  | x | x |  |  | x
3.4.3 | Q&A Moderation
| • Close Comments • Reply/remove Answers • Move one Q&A from one topic to another • Designate answer as best answer |  | x | x
3.4.4 | Flagged for concern content
| • Flagged content w/reason by flagger |  | x | x |  | x | x
| • Review content (reject if violates, mark as review if not) |  | x | x
Polls
| • Add, review and remove Polls |  | x | x
3.5 | Internal Users
3.5.2 | Add users and assign roles |  | x
3.5.3 | Remove/modify user permissions |  | x
3.6 | Reports
3.7 | External Users
3.7.2 | • View Member information (delete account, assign roll and etc) |  | x | x
3.7.3 | • Assign Badges manually |  | x | x
3.8 | Emails
3.9 | Expert UI
3.9.1 | Questions from Queue |  | x | x |  | x
| Add Expert roll to a user |  | x | x
Ask question
Vote
Answer Question
Follow CAT/question/tag
Add and Delete Tags

## UX Estimates
Feature | UX Hours | Copy Hours | Creative Hours | FED Hours | Total Hours per feature
Q&A (3.5, 3.6) | 140 | 16 | 130 | 55.5 | 341.5 | 60
Search (3.3) | 200 | 10 | 120 | 57.5 | 387.5 | 60
Homepage (3.3, 3.4. 3.12) (Needs to go to Design Review) | 330 | 48 | 310 | 120 | 808 | 200
Blog (3.10) | 80 | 8 | 90 | 20 | 198 | 160
Interest Page (3.9, 3.10, 3.11) | 200 | 24 | 220 | 45 | 489 | 60
Login/Registration (3.1, 3.2) | 60 | 24 | 132 | 80 | 296 | 200
Profile (3.1, 3.2, 3.3, 3.7 (logged in state), 3.13, 3.17) | 180 | 76 | 582 | 252.5 | 1090.5 | 250
Admin & MOD Tool (?) | 464 |  |  | 359 | 823
Total | 1654 | 206 | 1584 | 989.5 | 4433.5 | 990

## Risks
Item | Risk | Dependency
1 | Tight deadline because of View Points Contract | View Points
2 | Migration | View Points
3 | Late UX handoffs | UX
4 | Communities mysears.com/mykmart.com dependency. This could become big
5 | Sears Single Sign-On (SSO) | ENG
6 | LDAP | ENG

## Assumptions
Item | Assumption
1 | Migration off of view points is the overall strategic plan
2 | Question and Answers it the most important business objective
3 | Migration: Prerequisite: provide mapping of viewpoints category to new community platform categories/taxonomy. Low - them create a file dump via WXR, Medium - some exporter, High - custom batch. multiple files
4 | Design is satisfactory to the team.
5 | Code is reviewed.
6 | Story acceptance criteria is met.
7 | No p1 and p2 open jira's.
8 | QA/BA accepted/passed the story.

## Team Sizing
[9 empty] | 2012-08-29 |  |  | 2012-08-07 | Main | Iteration 1 | 12
| DRAFT | [7 empty] | 2012-09-12 |  |  | 2012-08-28 | Migration/UAT | Iteration 2 | 3 | Not counting release week
Project Start | 2012-05-21 | [7 empty] | 2012-09-26 |  |  | 2012-09-25 |  | Iteration 3 | 4 | Not counting release week
Project End | 2012-10-24 | [7 empty] | 2012-10-10 |  |  | 2012-10-23 |  | Iteration 4 | 4 | Not counting release week
[9 empty] | 2012-10-24 |  |  |  |  | Iteration 5 |  | traingin
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | Total FTE
Location | Track | 2012-05-21 | 2012-05-28 | 2012-06-04 | 2012-06-11 | 2012-06-18 | 2012-06-25 | 2012-07-02 | 2012-07-09 | 2012-07-16 | 2012-07-23 | 2012-07-30 | 2012-08-06 | 2012-08-13 | 2012-08-20 | 2012-08-27 | 2012-09-03 | 2012-09-10 | 2012-09-17 | 2012-09-24 | 2012-10-01 | 2012-10-08 | 2012-10-15 | 2012-10-22 | 2012-10-29 | 2012-11-05 | 2012-11-12 | 2012-11-19 | 2012-11-26 | Staffing
Oversight Roles
0
| Tech Lead | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 140
| Tech Lead | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 140
| Architect | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 32
172
Total Oversight Person Hours |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 0 | 22 | 0 | 22 | 268
Team Roles
| Engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 520
| Eng, Web Developer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 30 | 30 | 30 | 30 | 180
| Eng, QA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 30 | 30 | 30 | 30 | 180
| Business Analyst | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
Total Team Person Hours |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 60 | 60 | 60 | 60 | 360
Grand Total Person Hours |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 82 | 82 | 60 | 82 | 60 | 82 | 628
352000
Roles | Skills | 2012-05-21: Exp. Yrs; 2012-05-28: Nbr; 2012-06-04: Onsite/Offshore
Project/technical lead | Agile development, Status reporting, Team management, Web development, Java, MySQL | 2012-05-21: 8; 2012-05-28: 1; 2012-06-04: SHI
Sr. Developer | Java 1.5, Web development, Spring, Spring MVC, MySQL, JPA/Hibernate/JDBC, Agile development | 2012-05-21: 8; 2012-05-28: 4; 2012-06-04: Onsite
Architect | Java 1.5, Web development, Spring, Spring MVC, MySQL, JPA/Hibernate/JDBC | 2012-05-21: 8; 2012-05-28: 1; 2012-06-04: SHI
Developer | Java 1.5, Web development, Spring, Spring MVC, MySQL, JPA/Hibernate.JDBC | 2012-05-21: 5'; 2012-05-28: 8; 2012-06-04: SHI
Sr QA |  | 2012-05-28: 2; 2012-06-04: Onsite
QA | Manual testing, JIRA | 2012-05-28: 2; 2012-06-04: SHI
Automation QA | Silenium or any other automation tool | 2012-05-28: 1; 2012-06-04: SHI
T Business Analyst |  | 2012-05-28: 1; 2012-06-04: Onsite
Note on A8: Enter all oversight roles with associated percentage allocation (0-1) for each week of the project.

## Release Dates
DRAFT
Iteration Plan
Iteration | Start | Days | End | Size | Status | Release Date | Goal | Release