## Priority
2012-08-29
Home Page | This page provided by Judy
Search
Login
Profile
Q&A
Interest Page
Mod Tool
CMS
Customer Service
2012-09-12
Following
Social Share
Expert
Email
2012-09-26
Ad Units
Enhancing CMS
Refactoring
2012-10-10
Commenting outside of Q&A
Related Top Rated Products
Enhancing Q&A
Enhancing CMS
2012-10-24
Enhancing Mod Tool

## Product Backlog
|  | Total points | 132 |  | Hours per point
[5 empty] | Low | Hi
|  | Total Hrs (High) | 4224 | Best quality | 16 | 32
|  | Total Hrs (Average) | 3168 | Moderate
|  | Total Hrs Low) | 2112 | Aggressive
|  | Story point/points include | * Design is satisfactory to the team. * Code is reviewed. * Unit tests coverage is 80% or more. * Story acceptance criteria is met. * No p1 and p2 open jira's. * How to demo is clear/Demo'able. * QA/BA accepted/passed the story.
Req # | Story # | Epic | User Story | Track | Points | LOE in Hours Calculated |  |  | Priority | Notes
[6 empty] | Low | High | Average
| 1 | Community Site | Home page - Logged in/Logged out(Hero image, articles, QA activity, Twitter feed, total members) |  | 8 | 128 | 256 | 192
| 2 | Community Site | Q & A |  | 8 | 128 | 256 | 192 |  | (CPT) Custom Post Type post_type=question as a parent parent_post=0. (CPT) post_type=answer, parent_post={questionID}
| 3 | Community Site |  |  | 0 | 0 | 0 | 0
| 4 | Community Site | Blog |  | 3 | 48 | 96 | 72 |  | templates = single, archive, aside for video
| 5 | Community Site | User profile page (My discussions, photo, Interests, activity points/badges) |  | 5 | 80 | 160 | 120
| 5 | Community Site | User Admin Settings Page |  | 3 | 48 | 96 | 72 |  | Place where they can turn off (opt-out) of following
| 6 | Community Site | Articles (Guides) |  | 2 | 32 | 64 | 48
| 7 | Community Site | Ad units on pages | 2 | 3 | 48 | 96 | 72 |  | Use CQ5
| 8 | Community Site | Site search (discussions, articles, blogs, store pages) |  | 3 | 48 | 96 | 72 |  | Indexing of blog and store pages is new addition.
| 9 | Community Site | SSO |  | 5 | 80 | 160 | 120 |  | Profile/SSO will take care of validating and authenticating open id just like user/password
|  |  | User Login |  | 5 | 0 | 0 | 0
| 10 | Community Site | Feedback (Qualtrics) |  | 0 | 0 | 0 | 0
| 11 | Community Site | Contacts page |  | 1 | 16 | 32 | 24
| 12 | Community Site | Tag/filter content by site (mysears/mykmart) |  | 8 | 128 | 256 | 192 |  | Separate installation for each site.
| 13 | Community Site | Activity feed based on profile |  | 3 | 48 | 96 | 72 |  | Logic to aggregate data based on profile interest settings.
| 14 | Community Site |  |  | 0 | 0 | 0 | 0 |  | Use external service/framework to deal with this/
| 15 | Community Site | Flag user added content(comments, discussions) |  | 2 | 32 | 64 | 48
| 16 | Community Site | Share it functionality(discussion, articles) |  | 2 | 32 | 64 | 48
| 17 | Community site | Emails(weekly activity) | which phase | 1 | 16 | 32 | 24 |  | Integration with responsys
| 18 | Community site | Google analytics |  | 1 | 16 | 32 | 24
| 19 | Community site | Prafanity filter |  | 2 | 32 | 64 | 48
| 20 | Migration | Migrate forums |  | 5 | 80 | 160 | 120 |  | Prerequisite: provide mapping of viewpoints category to new community platform categories/taxonomy. Low - them create a file dump via WXR, Medium - some exporter, High - custom batch. multiple files
| 21 | Migration | Migrate articles |  | 3 | 48 | 96 | 72 |  | Prerequisite: provide mapping of viewpoints category to new community platform categories/taxonomy. Low - them create a file dump via WXR, Medium - some exporter, High - custom batch. multiple files
| 21 | Migration | Migrate blogs |  | 3 | 48 | 96 | 72 |  | Prerequisite: provide mapping of viewpoints category to new community platform categories/taxonomy. Low - them create a file dump via WXR, Medium - some exporter, High - custom batch. multiple files
Migrate User Info??
| 22 | Migration | Search index all migrated contents | ?? | 0 | 0 | 0 | 0 |  | Prerequisite: provide mapping of viewpoints category to new community platform categories/taxonomy. Low - them create a file dump via WXR, Medium - some exporter, High - custom batch. multiple files
| 23 | Misc | Setup data & taxonomy |  | 8 | 128 | 256 | 192 |  | This is step1 before building any functionality.
| 25 | Misc | Support old URL's redirects |  | 8 | 128 | 256 | 192 |  | Create support for OLD URL's toredirect to the new site URL's
| 24 | Misc | Architecture |  | 5 | 80 | 160 | 120 |  | Server setup. Cacheing
| 25 | Misc | Setup environments (Dev,QA,integration,Prod) |  | 3 | 48 | 96 | 72
| 26 | Misc | Performance testing |  | 3 | 48 | 96 | 72
| 27 | Misc | Continous integration environment |  | 1 | 16 | 32 | 24
| 28 | Misc | Iterative production releases |  | 5 | 80 | 160 | 120
| 29 | Misc | Meetings |  | 0 | 0 | 0 | 0
| 30 | Admin/moderation | Display flagged content & delete inappropriate entries(coments, questions) |  | 3 | 48 | 96 | 72
| 31 | Admin/moderation | Ldap login |  | 1 | 16 | 32 | 24
| 32 | CMS | Home page content mgmt. |  | 3 | 48 | 96 | 72 |  | Hero Image, Featured Article - (FA Lite)
| 33 | CMS | Author buying guides |  | 1 | 16 | 32 | 24
| 34 | CMS | Author blogs |  | 3 | 48 | 96 | 72
| 35 | CMS | Experts Q & A |  | 8 | 128 | 256 | 192
| 36 | Feeds | Syndication | 2 | 3 | 48 | 96 | 72
| 37 | Community site | Comments (Blogs, Articles) |  | 1 | 16 | 32 | 24
|  |  |  | Totals | 132 | 2032 | 4064 | 3048
Descoped
New Scope
Note on A9: The category to which this story belongs, if any.
Note on B9: The category to which this story belongs, if any.
Note on C9: The category to which this story belongs, if any.
Note on E9: If known, the Track that will deliver this story.
Note on F9: The Tech Story Points associated with this story. This value is translated into ABP/HP through velocity.