## Product backlog
| Total points | 137 |  | Hours per point
|  |  |  | Low | Hi
| Total Hrs (High) | 4384 | Best quality | 16 | 32
| Total Hrs (Average) | 3288 | Moderate
| Total Hrs Low) | 2192 | Aggressive
| Story point/points include | * Design is satisfactory to the team. * Code is reviewed. * Unit tests coverage is 80% or more. * Story acceptance criteria is met. * No p1 and p2 open jira's. * How to demo is clear/Demo'able. * QA/BA accepted/passed the story.
Story # | Epic | User Story | Track | Points | LOE in Hours Calculated |  |  | Priority | Notes
[5 empty] | Low | High | Average
1 | Community Site | Home page - Logged in/Logged out(Hero image, articles, QA activity, Twitter feed, total members) |  | 5 | 80 | 160 | 120
2 | Community Site | Discussions |  | 3 | 48 | 96 | 72 |  | Use MML Q/A
3 | Community Site | Static managed store pages | out | 2 | 32 | 64 | 48
4 | Community Site | Blog |  | 8 | 128 | 256 | 192 |  | New feature to be built suing MML articles function.
5 | Community Site | User profile page (Points, My reviews, My discussions, photo, Interests, activity points/badges) | everything except reviews. Reviews going to SYW. No points, but they want badges | 3 | 48 | 96 | 72 |  | Add on profile attributes live in MML/new communities user profile database.
5 | Community Site | User profile page get user preffered store and link to the store page | out | 5 | 80 | 160 | 120
6 | Community Site | Articles (Guides) |  | 2 | 32 | 64 | 48
7 | Community Site | Ad units on pages |  | 3 | 48 | 96 | 72 |  | Only ad display capability. ad-management is external to communities platform.
8 | Community Site | Site search (discussions, articles, blogs, store pages) |  | 3 | 48 | 96 | 72 |  | Indexing of blog and store pages is new addition.
9 | Community Site | Open ID integration (login) |  | 1 | 16 | 32 | 24 |  | Profile/SSO will take care of validating and authenticating open id just like user/password
10 | Community Site | Feedback (Qualtrics) |  | 0 | 0 | 0 | 0
11 | Community Site | Contacts page |  | 1 | 16 | 32 | 24 |  | Base reference story for estimates
12 | Community Site | Tag/filter content by site (mysears/mykmart) |  | 8 | 128 | 256 | 192 |  | Same db with site tag or separate installation for each site.
13 | Community Site | Activity feed based on profile |  | 3 | 48 | 96 | 72 |  | Logic to aggregate data based on profile interest settings.
14 | Community Site | Events & RSVP | out | 8 | 128 | 256 | 192 |  | Use external service/framework to deal with this/
15 | Community Site | Flag user added content(comments, discussions) |  | 2 | 32 | 64 | 48
16 | Community Site | Share it functionality(discussion, articles) |  | 2 | 32 | 64 | 48
17 | Community site | Emails(weekly activity) |  | 1 | 16 | 32 | 24 |  | Integration with responsys
18 | Community site | Google analytics |  | 1 | 16 | 32 | 24
19 | Community site | Prafanity filter |  | 2 | 32 | 64 | 48
20 | Migration | Migrate forums |  | 5 | 80 | 160 | 120 |  | Prerequisite: rovide mapping of viewpoints category to new community platform categories/taxonomy.
21 | Migration | Migrate articles |  | 3 | 48 | 96 | 72 |  | Prerequisite: rovide mapping of viewpoints category to new community platform categories/taxonomy.
21 | Migration | Migrate blogs |  | 3 | 48 | 96 | 72 |  | Prerequisite: rovide mapping of viewpoints category to new community platform categories/taxonomy.
22 | Migration | Search index all migrated contents |  | 8 | 128 | 256 | 192 |  | Prerequisite: rovide mapping of viewpoints category to new community platform categories/taxonomy.
23 | Misc | Setup MML for communities(data, taxonomy, mml software) |  | 8 | 128 | 256 | 192 |  | This is step1 before building any functionality.
25 | Misc | Support old URL's redirects |  | 8 | 128 | 256 | 192 |  | Create support for OLD URL's toredirect to the new site URL's
24 | Misc | Architecture |  | 5 | 80 | 160 | 120
25 | Misc | Setup environments (Dev,QA,integration,Prod) |  | 3 | 48 | 96 | 72
26 | Misc | Performance testing |  | 3 | 48 | 96 | 72
27 | Misc | Continous integration environment |  | 1 | 16 | 32 | 24
28 | Misc | Iterative production releases |  | 5 | 80 | 160 | 120
29 | Misc | Meetings |  | 0 | 0 | 0 | 0
30 | Admin/moderation | Display flagged content & delete inappropriate entries(coments, questions) |  | 3 | 48 | 96 | 72
31 | Admin/moderation | Ldap login |  | 1 | 16 | 32 | 24
32 | CMS | Home page content mgmt. |  | 3 | 48 | 96 | 72
33 | CMS | Author buying guides |  | 1 | 16 | 32 | 24
34 | CMS | Author blogs |  | 3 | 48 | 96 | 72
35 | CMS | Create and administer store pages | out | 8 | 128 | 256 | 192
36 | Feeds | WCS store locater links | out | 2 | 32 | 64 | 48
37 | Community site | Comments (Blogs, Articles) |  | 1 | 16 | 32 | 24 |  | Functionality already built, but disabled on MML>
|  |  | Totals | 137 | 2192 | 4384 | 3288
Descoped
New Scope
Note on A9: The category to which this story belongs, if any.
Note on B9: The category to which this story belongs, if any.
Note on D9: If known, the Track that will deliver this story.
Note on E9: The Tech Story Points associated with this story. This value is translated into ABP/HP through velocity.

## Team sizing
Project Start | 2012-01-17
Project End | 2012-05-22
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | Total FTE
Location | Track | 2012-01-17 | 2012-01-24 | 2012-01-31 | 2012-02-07 | 2012-02-14 | 2012-02-21 | 2012-02-28 | 2012-03-06 | 2012-03-13 | 2012-03-20 | 2012-03-27 | 2012-04-03 | 2012-04-10 | 2012-04-17 | 2012-04-24 | 2012-05-01 | 2012-05-08 | 2012-05-15 | 2012-05-22 | 2012-05-29 | 2012-06-05 | 2012-06-12 | 2012-06-19 | 2012-06-26 | 2012-07-03 | 2012-07-10 | 2012-07-17 | 2012-07-24 | 2012-07-31 | 2012-08-07 | 2012-08-14 | 2012-08-21 | 2012-08-28 | 2012-09-04 | 2012-09-11 | 2012-09-18 | 2012-09-25 | 2012-10-02 | 2012-10-09 | 2012-10-16 | 2012-10-23 | Staffing
Oversight Roles
0 | bar: 29
| T-Tech Lead | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190
| T-Tech Lead | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190
| Architect | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42
232 | bar: 29
Total Oversight Person Hours |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 0 | 22 | 0 | 22 | 0 | 22 | 22 | 22 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 356
Team Roles
| T-Engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720
| T-Engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720
| T-Engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720
| T-Engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720
| T-Engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720
| T-Engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720
| T-Engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720
| T-Engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720
| T-QA Engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330
| T-QA Engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330
| T-Business Analyst | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
0 | bar: 29
Total Team Person Hours |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4980
Grand Total Person Hours |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 22 | 262 | 262 | 262 | 262 | 262 | 262 | 262 | 322 | 322 | 300 | 322 | 300 | 322 | 300 | 322 | 322 | 322 | 322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5336
352000
Roles | Skills | 1: Exp. Yrs; 2: Nbr; 3: Onsite/Offshore
Project/technical lead | Agile development, Status reporting, Team management, Web development, Java, MySQL | 1: 8; 2: 1; 3: SHI
Sr. Developer | Java 1.5, Web development, Spring, Spring MVC, MySQL, JPA/Hibernate/JDBC, Agile development | 1: 8; 2: 4; 3: Onsite
Architect | Java 1.5, Web development, Spring, Spring MVC, MySQL, JPA/Hibernate/JDBC | 1: 8; 2: 1; 3: SHI
Developer | Java 1.5, Web development, Spring, Spring MVC, MySQL, JPA/Hibernate.JDBC | 1: 5'; 2: 8; 3: SHI
Sr QA |  | 2: 2; 3: Onsite
QA | Manual testing, JIRA | 2: 2; 3: SHI
Automation QA | Silenium or any other automation tool | 2: 1; 3: SHI
T Business Analyst |  | 2: 1; 3: Onsite
Note on A8: Enter all oversight roles with associated percentage allocation (0-1) for each week of the project.

## Pritized epic list
Dates(from - to) | Prioritized list

## Iteration and release dates
Release Plan
Incr. | Start | Days | End | Size | Status | Release Date | Goal
1 | 2012-05-01 | 14 | 2012-05-14 | #VALUE!
2 | 2012-05-15 | 14 | 2012-05-28 | #VALUE!
3 |  | 14 |  | #VALUE!
4 |  | 14 |  | 3
5 |  | 14 |  | #VALUE!
6 |  | 14 |  | 2
7 |  | 14
8 |  | 14
9 |  | 14
10 |  | 14 |  | #VALUE!
Iteration Plan
Iteration | Start | Days | End | Size | Status | Release Date | Goal | Release
1 | 2012-05-01 | 14 | 2012-05-14 | #VALUE! | Planned |  |  | 1
2 | 2012-05-15 | 14 | 2012-05-28 | #VALUE! | Planned |  |  | 2
3 | 2012-05-29 | 14 | 2012-06-11 | #VALUE! | Planned |  |  | 3
4 | 2012-06-12 | 14 | 2012-06-25 | 3 | Planned |  |  | 4
5 | 2012-06-26 | 14 | 2012-07-09 | #VALUE! | Planned |  |  | 5
6 | 2012-07-10 | 14 | 2012-07-23 | 2 | Planned |  |  | 6
7 | 2012-07-24 | 14 | 2012-08-06 | #VALUE! | Planned |  |  | 7
8 | 2012-08-07 | 14 | 2012-08-20 | #VALUE! | Planned |  |  | 8
9 | 2012-08-21 | 14 | 2012-09-03 | #VALUE! | Planned |  |  | 9
10 | 2012-09-04 | 14 | 2012-09-17 | #VALUE! | Planned |  |  | 10
11 | 2012-09-18 | 14 | 2012-10-01 | #VALUE! | Planned
Formulas:
Start = IF(OR(B18="",[Incr.]=""),"",B18)
Start = IF([Incr.]="","",[Start, row above]+[Days, row above])
End = IF(OR([Start]="",[Days]=""),"",[Start]+[Days]-1)
End = IF(AND([Start]<>"",[Days]<>""),[Start]+[Days]-1,"")

## Risks
S. No. | Risk
1 | Late start due to delay in funding. It will impact the release date
2 | Diverse teams integrating with the service each possibly running at different pace
3 | Data migration from view points. This depends on how much support is provided by view points.
4 | Communities mysears.com/mykmart.com dependency. This could become big