## Summary
Iteration | 1 | 2 | 3 | 4 | 5 | Totals
Launch Date | 2012-08-06 | 2012-08-27 | 2012-09-17 | 2012-10-08 | 2012-10-29
Eng Estimate | 1900 | 450 | 450 | 200 | 100 | 3100
FED Estimate | 480 | 120 | 120 | 120 | 120 | 960
BA | 285 | 78 | 78 | 78 | 78 | 597
QA | 700 | 190 | 190 | 190 | 190 | 1460
Training | 40 | 60 | 20 | 20 | 0 | 140
Total Estimate | 3405 | 898 | 858 | 608 | 488 | 6257

## Estimate
| Total points | 174 |  | Hours per point
|  |  |  | Low | Hi
| Total Hrs (High) | 5568 | Best quality | 16 | 32
| Total Hrs (Average) | 4176 | Moderate
| Total Hrs Low) | 2784 | Aggressive
Track Total Hours
LOE in Hours Calculated
Story # | Epic | User Story | Track | Points | Low | High | Average | UX Priority | Eng Priority | Dependency | Notes |  | Low | High | High | High | High | Low | Low | Low | Low | Low | Avg | Avg | Avg | Avg | Avg
[13 empty] | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5
1 | Community Site | Home page - Logged in/Logged out(Hero image, articles, QA activity, Twitter feed, total members) | 1 | 8 | 128 | 256 | 192 | 1 |  |  |  |  | 128 | 0 | 0 | 0 | 0 | 128 | 0 | 0 | 0 | 0 | 192 | 0 | 0 | 0 | 0
2 | Community Site | Q & A (discussions) | 1 | 8 | 128 | 256 | 192 | 2 |  |  | (CPT) Custom Post Type post_type=question as a parent parent_post=0. (CPT) post_type=answer, parent_post={questionID} |  | 128 | 0 | 0 | 0 | 0 | 128 | 0 | 0 | 0 | 0 | 192 | 0 | 0 | 0 | 0
3 | Community Site | Blog | 1 | 3 | 48 | 96 | 72 | 1 |  |  | templates = single, archive, aside for video |  | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0
4 | Community Site | User profile page (My discussions, photo, Interests, badges) | 1 | 5 | 80 | 160 | 120 | 2 |  |  |  |  | 80 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0
5 | Community Site | User Admin Settings Page | 1 | 3 | 48 | 96 | 72 | 4 |  |  | Place where they can turn off (opt-out) of following |  | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0
6 | Community Site | Articles (Guides) | 1 | 2 | 32 | 64 | 48 | 3 |  |  |  |  | 32 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0
7 | Community Site | Ad units on pages | 4 | 5 | 80 | 160 | 120 | 0 |  |  | Use CQ5 |  | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 120 | 0
8 | Community Site | Site search (discussions, articles, blogs) | 1 | 3 | 48 | 96 | 72 | 3 |  |  | Indexing of blog and store pages is new addition. |  | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0
9 | Community Site | Site Search - Auto Complete | 5 | 8 | 128 | 256 | 192 | 0 |  |  | will require mongo DB |  | 0 | 0 | 0 | 0 | 256 | 0 | 0 | 0 | 0 | 128 | 0 | 0 | 0 | 0 | 192
10 | Community Site | SSO | 1 | 5 | 80 | 160 | 120 | 0 |  |  | Profile/SSO will take care of validating and authenticating open id just like user/password |  | 80 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0
11 | Community Site | User Login | 1 | 5 | 80 | 160 | 120 | 2 |  |  |  |  | 80 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0
12 | Community Site | Feedback (Qualtrics) | 3 | 1 | 16 | 32 | 24 | 0 |  |  |  |  | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 24 | 0 | 0
13 | Community Site | Contacts page | 1 | 1 | 16 | 32 | 24 | 5 |  |  |  |  | 16 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0
14 | Community Site | Tag/filter content by site (mysears/mykmart) | 1 | 8 | 128 | 256 | 192 | 2 |  |  | Separate installation for each site. Double UX work |  | 128 | 0 | 0 | 0 | 0 | 128 | 0 | 0 | 0 | 0 | 192 | 0 | 0 | 0 | 0
15 | Community Site | Activity feed based on profile | 1 | 3 | 48 | 96 | 72 | 0 |  |  | Logic to aggregate data based on profile interest settings. |  | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0
16 | Community Site | Voting and Flagging | 4 | 2 | 32 | 64 | 48 | 3 |  |  |  |  | 0 | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 48 | 0
17 | Community Site | Share it functionality(discussion, articles) | 2 | 2 | 32 | 64 | 48 | 1 |  |  | Add This |  | 0 | 64 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0
18 | Community site | Emails Responsys Integration | 3 | 5 | 80 | 160 | 120 | 10 |  |  | Integration with responsys |  | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 120 | 0 | 0
19 | Community site | Google analytics | 1 | 1 | 16 | 32 | 24 | 0 |  |  |  |  | 16 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0
20 | Community site | Prafanity filter | 2 | 2 | 32 | 64 | 48 | 0 |  |  |  |  | 0 | 64 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0
21 | Community site | Interest Page - Customer Service | 1 | 5 | 80 | 160 | 120 | 0 |  |  |  |  | 80 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0
22 | Community site | Interest Page - 2 Category Template Page | 1 | 3 | 48 | 96 | 72 | 0 |  |  |  |  | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0
23 | Community site | Comments (Blogs, Articles) | 1 | 1 | 16 | 32 | 24 | 6 |  |  |  |  | 16 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0
24 | Migration | Migrate forums | 1 | 5 | 80 | 160 | 120 | 0 |  |  | View Points provides conversion data |  | 80 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0
25 | Migration | Migrate articles | 2 | 3 | 48 | 96 | 72 | 0 |  |  | View Points provides conversion data |  | 0 | 96 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0
26 | Migration | Migrate blogs | 2 | 3 | 48 | 96 | 72 | 0 |  |  | View Points provides conversion data |  | 0 | 96 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0
27 | Migration | Migrate User Info | 2 | 5 | 80 | 160 | 120 | 0 |  |  | View Points provides conversion data |  | 0 | 160 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0
28 | Migration | Search index all migrated contents | 3 | 5 | 80 | 160 | 120 | 0 |  |  | View Points provides conversion data |  | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 120 | 0 | 0
29 | Misc | Setup data & taxonomy | 1 | 8 | 128 | 256 | 192 | 1 |  |  | This is step1 before building any functionality. |  | 128 | 0 | 0 | 0 | 0 | 128 | 0 | 0 | 0 | 0 | 192 | 0 | 0 | 0 | 0
30 | Misc | Support old URL's redirects | 1 | 8 | 128 | 256 | 192 | 0 |  |  | Create support for OLD URL's toredirect to the new site URL's |  | 128 | 0 | 0 | 0 | 0 | 128 | 0 | 0 | 0 | 0 | 192 | 0 | 0 | 0 | 0
31 | Misc | Architecture | 3 | 5 | 80 | 160 | 120 | 0 |  |  | Server setup. Cacheing |  | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 120 | 0 | 0
32 | Misc | Setup environments (Dev,QA,integration,Prod) | 1 | 3 | 48 | 96 | 72 | 0 |  |  |  |  | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0
33 | Misc | Performance testing | 1 | 3 | 48 | 96 | 72 | 0 |  |  |  |  | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0
34 | Misc | Continous integration environment | 1 | 1 | 16 | 32 | 24 | 0 |  |  |  |  | 16 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0
35 | Misc | Iterative production releases 1 | 1 | 1 | 16 | 32 | 24 | 0 |  |  |  |  | 16 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0
36 | Misc | Iterative production releases 2 | 2 | 1 | 16 | 32 | 24 | 0 |  |  |  |  | 0 | 32 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0
37 | Misc | Iterative production releases 3 | 3 | 1 | 16 | 32 | 24 | 0 |  |  |  |  | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 24 | 0 | 0
38 | Misc | Iterative production releases 4 | 4 | 1 | 16 | 32 | 24 | 0 |  |  |  |  | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 24 | 0
39 | Misc | Iterative production releases 5 | 5 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | Misc | Meetings Iteration 1 | 1 | 2 | 32 | 64 | 48 | 0 |  |  |  |  | 32 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0
41 | Misc | Meetings Iteration 2 | 2 | 2 | 32 | 64 | 48 | 0 |  |  |  |  | 0 | 64 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0
42 | Misc | Meetings Iteration 3 | 3 | 2 | 32 | 64 | 48 | 0 |  |  |  |  | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 48 | 0 | 0
43 | Misc | Meetings Iteration 4 | 4 | 2 | 32 | 64 | 48 | 0 |  |  |  |  | 0 | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 48 | 0
44 | Misc | Meetings Iteration 5 | 5 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | Admin/moderation | Display flagged content & delete inappropriate entries(coments, questions) | 1 | 3 | 48 | 96 | 72 | 6 |  |  |  |  | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0
46 | Admin/moderation | Ldap login | 1 | 1 | 16 | 32 | 24 | 6 |  |  |  |  | 16 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0
47 | Admin/moderation | Reporting | 4 | 2 | 32 | 64 | 48 | 6 |  |  |  |  | 0 | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 48 | 0
48 | CMS | Home page content mgmt. | 1 | 3 | 48 | 96 | 72 | 6 |  |  | Hero Image, Featured Article - (FA Lite) |  | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0
49 | CMS | Author buying guides | 1 | 1 | 16 | 32 | 24 | 6 |  |  |  |  | 16 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0
50 | CMS | Author blogs | 1 | 3 | 48 | 96 | 72 | 6 |  |  |  |  | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0
51 | CMS | Experts Q & A | 1 | 8 | 128 | 256 | 192 | 6 |  |  |  |  | 128 | 0 | 0 | 0 | 0 | 128 | 0 | 0 | 0 | 0 | 192 | 0 | 0 | 0 | 0
52 | Feeds | Syndication | 3 | 3 | 48 | 96 | 72 | 0 |  |  |  |  | 0 | 0 | 96 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 72 | 0 | 0
53 | Resource | FED Iteration 1 | 1 | 30 | 480 | 960 | 720 | 0 |  |  |  |  | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 0 | 0 | 0 | 720 | 0 | 0 | 0 | 0
54 | Resource | FED Iteration 2 | 2 | 10 | 160 | 320 | 240 | 0 |  |  |  |  | 0 | 320 | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0
55 | Resource | FED Iteration 3 | 3 | 5 | 80 | 160 | 120 | 0 |  |  |  |  | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 120 | 0 | 0
56 | Resource | FED Iteration 4 | 4 | 5 | 80 | 160 | 120 | 0 |  |  |  |  | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 120 | 0
57 | Resource | FED Iteration 5 | 5 | 5 | 80 | 160 | 120 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 120
| Community Site | Manuals | 5 | 8 | 128 | 256 | 192 | 0
| Community Site | Following | 2 | 2 | 32 | 64 | 48 | 0
| Community Site | Polls | 4 | 3 | 48 | 96 | 72 | 0
[13 empty] | Low | High | High | High | High | Low | Low | Low | Low | Low | Avg | Avg | Avg | Avg | Avg
|  |  | Totals | 242 | 3872 | 7744 | 5808 |  |  |  |  | Total Hours | 2304 | 896 | 864 | 544 | 416 | 2304 | 448 | 432 | 272 | 208 | 3456 | 672 | 648 | 408 | 312
[12 empty] | Weeks | 64 | 24.8889 | 24 | 15.1111 | 11.5556 | 64 | 12.4444 | 12 | 7.5556 | 5.7778 | 96 | 18.6667 | 18 | 11.3333 | 8.6667
[12 empty] | Actual Weeks | 12 | 3 | 3 | 3 | 3 | 12 | 3 | 3 | 3 | 3 | 12 | 3 | 3 | 3 | 3
[12 empty] | # of Dev | 5.3333 | 8.2963 | 8 | 5.037 | 3.8519 | 5.3333 | 4.1481 | 4 | 2.5185 | 1.9259 | 8 | 6.2222 | 6 | 3.7778 | 2.8889
[12 empty] | Grand Total Hours |  |  |  |  | 5024 |  |  |  |  | 3664 |  |  |  |  | 5496
Final Estimate
[12 empty] | Iteration 1 | low | 2304
[12 empty] | Iteration 2-4 | avg | 2040
[12 empty] | QA |  | 1440
[12 empty] | BA |  | 600
[12 empty] | Training |  | 160
[12 empty] | Total |  | 6384
Note on A9: The category to which this story belongs, if any.
Note on B9: The category to which this story belongs, if any.
Note on D9: If known, the Track that will deliver this story.
Note on E9: The Tech Story Points associated with this story. This value is translated into ABP/HP through velocity.

## Risks
Item | Risk | Dependency
1 | Tight deadline because of View Points Contract | View Points
2 | Migration | View Points
3 | Late UX handoffs | UX
4 | Communities mysears.com/mykmart.com dependency. This could become big
5 | Sears Single Sign-On (SSO) | ENG
6 | LDAP | ENG

## Assumptions
Item | Assumption
1 | Migration off of view points is the overall strategic plan
2 | Question and Answers it the most important business objective
3 | Migration: Prerequisite: provide mapping of viewpoints category to new community platform categories/taxonomy. Low - them create a file dump via WXR, Medium - some exporter, High - custom batch. multiple files
4 | Design is satisfactory to the team.
5 | Code is reviewed.
6 | Story acceptance criteria is met.
7 | No p1 and p2 open jira's.
8 | QA/BA accepted/passed the story.