## Summary
Iteration | 1 | 2 | 3 | 4 | 5 | Totals
Launch Date | 2012-08-06 | 2012-08-27 | 2012-09-17 | 2012-10-08 | 2012-10-29
Eng Estimate | 1900 | 450 | 450 | 200 | 100 | 3100
FED Estimate | 480 | 120 | 120 | 120 | 120 | 960
BA | 285 | 78 | 78 | 78 | 78 | 597
QA | 700 | 190 | 190 | 190 | 190 | 1460
Training | 40 | 60 | 20 | 20 | 0 | 140
Total Estimate | 3405 | 898 | 858 | 608 | 488 | 6257

## Estimate
| Total points | 174 |  | Hours per point
|  |  |  | Low | Hi
| Total Hrs (High) | 5568 | Best quality | 16 | 32
| Total Hrs (Average) | 4176 | Moderate
| Total Hrs Low) | 2784 | Aggressive
Track Total Hours
LOE in Hours Calculated
Story # | Epic | User Story | Track | Points | Low | High | Average | UX Priority | Eng Priority | Dependency | Notes |  | Low | High | High | High | High |  | Low | Low | Low | Low | Low | Avg | Avg | Avg | Avg | Avg
[13 empty] | 1 | 2 | 3 | 4 | 5 |  | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5
1 | Community Site | Home page - Logged in/Logged out(Hero image, articles, QA activity, Twitter feed, total members) | 1 | 8 | 128 | 256 | 192 | 1 |  |  |  |  | 128 | 0 | 0 | 0 | 0 |  | 128 | 0 | 0 | 0 | 0 | 192 | 0 | 0 | 0 | 0
2 | Community Site | Q & A (discussions) | 1 | 8 | 128 | 256 | 192 | 2 |  |  | (CPT) Custom Post Type post_type=question as a parent parent_post=0. (CPT) post_type=answer, parent_post={questionID} |  | 128 | 0 | 0 | 0 | 0 |  | 128 | 0 | 0 | 0 | 0 | 192 | 0 | 0 | 0 | 0
3 | Community Site | Blog | 1 | 3 | 48 | 96 | 72 | 1 |  |  | templates = single, archive, aside for video |  | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0
4 | Community Site | User profile page (My discussions, photo, Interests, badges) | 1 | 5 | 80 | 160 | 120 | 2 |  |  |  |  | 80 | 0 | 0 | 0 | 0 |  | 80 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0
5 | Community Site | User Admin Settings Page | 1 | 3 | 48 | 96 | 72 | 4 |  |  | Place where they can turn off (opt-out) of following |  | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0
6 | Community Site | Articles (Guides) | 1 | 2 | 32 | 64 | 48 | 3 |  |  |  |  | 32 | 0 | 0 | 0 | 0 |  | 32 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0
7 | Community Site | Ad units on pages | 4 | 5 | 80 | 160 | 120 | 0 |  |  | Use CQ5 |  | 0 | 0 | 0 | 160 | 0 |  | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 120 | 0
8 | Community Site | Site search (discussions, articles, blogs) | 1 | 3 | 48 | 96 | 72 | 3 |  |  | Indexing of blog and store pages is new addition. |  | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0
9 | Community Site | Site Search - Auto Complete | 5 | 8 | 128 | 256 | 192 | 0 |  |  | will require mongo DB |  | 0 | 0 | 0 | 0 | 256 |  | 0 | 0 | 0 | 0 | 128 | 0 | 0 | 0 | 0 | 192
10 | Community Site | SSO | 1 | 5 | 80 | 160 | 120 | 0 |  |  | Profile/SSO will take care of validating and authenticating open id just like user/password |  | 80 | 0 | 0 | 0 | 0 |  | 80 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0
11 | Community Site | User Login | 1 | 5 | 80 | 160 | 120 | 2 |  |  |  |  | 80 | 0 | 0 | 0 | 0 |  | 80 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0
12 | Community Site | Feedback (Qualtrics) | 3 | 1 | 16 | 32 | 24 | 0 |  |  |  |  | 0 | 0 | 32 | 0 | 0 |  | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 24 | 0 | 0
13 | Community Site | Contacts page | 1 | 1 | 16 | 32 | 24 | 5 |  |  |  |  | 16 | 0 | 0 | 0 | 0 |  | 16 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0
14 | Community Site | Tag/filter content by site (mysears/mykmart) | 1 | 8 | 128 | 256 | 192 | 2 |  |  | Separate installation for each site. Double UX work |  | 128 | 0 | 0 | 0 | 0 |  | 128 | 0 | 0 | 0 | 0 | 192 | 0 | 0 | 0 | 0
15 | Community Site | Activity feed based on profile | 1 | 3 | 48 | 96 | 72 | 0 |  |  | Logic to aggregate data based on profile interest settings. |  | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0
16 | Community Site | Voting and Flagging | 4 | 2 | 32 | 64 | 48 | 3 |  |  |  |  | 0 | 0 | 0 | 64 | 0 |  | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 48 | 0
17 | Community Site | Share it functionality(discussion, articles) | 2 | 2 | 32 | 64 | 48 | 1 |  |  | Add This |  | 0 | 64 | 0 | 0 | 0 |  | 0 | 32 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0
18 | Community site | Emails Responsys Integration | 3 | 5 | 80 | 160 | 120 | 10 |  |  | Integration with responsys |  | 0 | 0 | 160 | 0 | 0 |  | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 120 | 0 | 0
19 | Community site | Google analytics | 1 | 1 | 16 | 32 | 24 | 0 |  |  |  |  | 16 | 0 | 0 | 0 | 0 |  | 16 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0
20 | Community site | Prafanity filter | 2 | 2 | 32 | 64 | 48 | 0 |  |  |  |  | 0 | 64 | 0 | 0 | 0 |  | 0 | 32 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0
21 | Community site | Interest Page - Customer Service | 1 | 5 | 80 | 160 | 120 | 0 |  |  |  |  | 80 | 0 | 0 | 0 | 0 |  | 80 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0
22 | Community site | Interest Page - 2 Category Template Page | 1 | 3 | 48 | 96 | 72 | 0 |  |  |  |  | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0
23 | Community site | Comments (Blogs, Articles) | 1 | 1 | 16 | 32 | 24 | 6 |  |  |  |  | 16 | 0 | 0 | 0 | 0 |  | 16 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0
24 | Migration | Migrate forums | 1 | 5 | 80 | 160 | 120 | 0 |  |  | View Points provides conversion data |  | 80 | 0 | 0 | 0 | 0 |  | 80 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0
25 | Migration | Migrate articles | 2 | 3 | 48 | 96 | 72 | 0 |  |  | View Points provides conversion data |  | 0 | 96 | 0 | 0 | 0 |  | 0 | 48 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0
26 | Migration | Migrate blogs | 2 | 3 | 48 | 96 | 72 | 0 |  |  | View Points provides conversion data |  | 0 | 96 | 0 | 0 | 0 |  | 0 | 48 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0
27 | Migration | Migrate User Info | 2 | 5 | 80 | 160 | 120 | 0 |  |  | View Points provides conversion data |  | 0 | 160 | 0 | 0 | 0 |  | 0 | 80 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0
28 | Migration | Search index all migrated contents | 3 | 5 | 80 | 160 | 120 | 0 |  |  | View Points provides conversion data |  | 0 | 0 | 160 | 0 | 0 |  | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 120 | 0 | 0
29 | Misc | Setup data & taxonomy | 1 | 8 | 128 | 256 | 192 | 1 |  |  | This is step1 before building any functionality. |  | 128 | 0 | 0 | 0 | 0 |  | 128 | 0 | 0 | 0 | 0 | 192 | 0 | 0 | 0 | 0
30 | Misc | Support old URL's redirects | 1 | 8 | 128 | 256 | 192 | 0 |  |  | Create support for OLD URL's toredirect to the new site URL's |  | 128 | 0 | 0 | 0 | 0 |  | 128 | 0 | 0 | 0 | 0 | 192 | 0 | 0 | 0 | 0
31 | Misc | Architecture | 3 | 5 | 80 | 160 | 120 | 0 |  |  | Server setup. Cacheing |  | 0 | 0 | 160 | 0 | 0 |  | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 120 | 0 | 0
32 | Misc | Setup environments (Dev,QA,integration,Prod) | 1 | 3 | 48 | 96 | 72 | 0 |  |  |  |  | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0
33 | Misc | Performance testing | 1 | 3 | 48 | 96 | 72 | 0 |  |  |  |  | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0
34 | Misc | Continous integration environment | 1 | 1 | 16 | 32 | 24 | 0 |  |  |  |  | 16 | 0 | 0 | 0 | 0 |  | 16 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0
35 | Misc | Iterative production releases 1 | 1 | 1 | 16 | 32 | 24 | 0 |  |  |  |  | 16 | 0 | 0 | 0 | 0 |  | 16 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0
36 | Misc | Iterative production releases 2 | 2 | 1 | 16 | 32 | 24 | 0 |  |  |  |  | 0 | 32 | 0 | 0 | 0 |  | 0 | 16 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0
37 | Misc | Iterative production releases 3 | 3 | 1 | 16 | 32 | 24 | 0 |  |  |  |  | 0 | 0 | 32 | 0 | 0 |  | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 24 | 0 | 0
38 | Misc | Iterative production releases 4 | 4 | 1 | 16 | 32 | 24 | 0 |  |  |  |  | 0 | 0 | 0 | 32 | 0 |  | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 24 | 0
39 | Misc | Iterative production releases 5 | 5 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | Misc | Meetings Iteration 1 | 1 | 2 | 32 | 64 | 48 | 0 |  |  |  |  | 32 | 0 | 0 | 0 | 0 |  | 32 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0
41 | Misc | Meetings Iteration 2 | 2 | 2 | 32 | 64 | 48 | 0 |  |  |  |  | 0 | 64 | 0 | 0 | 0 |  | 0 | 32 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0
42 | Misc | Meetings Iteration 3 | 3 | 2 | 32 | 64 | 48 | 0 |  |  |  |  | 0 | 0 | 64 | 0 | 0 |  | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 48 | 0 | 0
43 | Misc | Meetings Iteration 4 | 4 | 2 | 32 | 64 | 48 | 0 |  |  |  |  | 0 | 0 | 0 | 64 | 0 |  | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 48 | 0
44 | Misc | Meetings Iteration 5 | 5 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | Admin/moderation | Display flagged content & delete inappropriate entries(coments, questions) | 1 | 3 | 48 | 96 | 72 | 6 |  |  |  |  | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0
46 | Admin/moderation | Ldap login | 1 | 1 | 16 | 32 | 24 | 6 |  |  |  |  | 16 | 0 | 0 | 0 | 0 |  | 16 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0
47 | Admin/moderation | Reporting | 4 | 2 | 32 | 64 | 48 | 6 |  |  |  |  | 0 | 0 | 0 | 64 | 0 |  | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 48 | 0
48 | CMS | Home page content mgmt. | 1 | 3 | 48 | 96 | 72 | 6 |  |  | Hero Image, Featured Article - (FA Lite) |  | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0
49 | CMS | Author buying guides | 1 | 1 | 16 | 32 | 24 | 6 |  |  |  |  | 16 | 0 | 0 | 0 | 0 |  | 16 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0
50 | CMS | Author blogs | 1 | 3 | 48 | 96 | 72 | 6 |  |  |  |  | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0
51 | CMS | Experts Q & A | 1 | 8 | 128 | 256 | 192 | 6 |  |  |  |  | 128 | 0 | 0 | 0 | 0 |  | 128 | 0 | 0 | 0 | 0 | 192 | 0 | 0 | 0 | 0
52 | Feeds | Syndication | 3 | 3 | 48 | 96 | 72 | 0 |  |  |  |  | 0 | 0 | 96 | 0 | 0 |  | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 72 | 0 | 0
53 | Resource | FED Iteration 1 | 1 | 30 | 480 | 960 | 720 | 0 |  |  |  |  | 480 | 0 | 0 | 0 | 0 |  | 480 | 0 | 0 | 0 | 0 | 720 | 0 | 0 | 0 | 0
54 | Resource | FED Iteration 2 | 2 | 10 | 160 | 320 | 240 | 0 |  |  |  |  | 0 | 320 | 0 | 0 | 0 |  | 0 | 160 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0
55 | Resource | FED Iteration 3 | 3 | 5 | 80 | 160 | 120 | 0 |  |  |  |  | 0 | 0 | 160 | 0 | 0 |  | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 120 | 0 | 0
56 | Resource | FED Iteration 4 | 4 | 5 | 80 | 160 | 120 | 0 |  |  |  |  | 0 | 0 | 0 | 160 | 0 |  | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 120 | 0
57 | Resource | FED Iteration 5 | 5 | 5 | 80 | 160 | 120 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 160 |  | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 120
| Community Site | Manuals | 5 | 8 | 128 | 256 | 192 | 0
| Community Site | Following | 2 | 2 | 32 | 64 | 48 | 0
| Community Site | Polls | 4 | 3 | 48 | 96 | 72 | 0
[13 empty] | Low | High | High | High | High |  | Low | Low | Low | Low | Low | Avg | Avg | Avg | Avg | Avg
|  |  | Totals | 242 | 3872 | 7744 | 5808 |  |  |  |  | Total Hours | 2304 | 896 | 864 | 544 | 416 |  | 2304 | 448 | 432 | 272 | 208 | 3456 | 672 | 648 | 408 | 312
[12 empty] | Weeks | 64 | 24.8889 | 24 | 15.1111 | 11.5556 |  | 64 | 12.4444 | 12 | 7.5556 | 5.7778 | 96 | 18.6667 | 18 | 11.3333 | 8.6667
[12 empty] | Actual Weeks | 12 | 3 | 3 | 3 | 3 |  | 12 | 3 | 3 | 3 | 3 | 12 | 3 | 3 | 3 | 3
[12 empty] | # of Dev | 5.3333 | 8.2963 | 8 | 5.037 | 3.8519 |  | 5.3333 | 4.1481 | 4 | 2.5185 | 1.9259 | 8 | 6.2222 | 6 | 3.7778 | 2.8889
[12 empty] | Grand Total Hours |  |  |  |  | 5024 | [5 empty] | 3664 |  |  |  |  | 5496
Final Estimate
[12 empty] | Iteration 1 | low | 2304 |  |  |  | 2304
[12 empty] | Iteration 2-4 | avg | 2040 |  |  |  | 1600
[12 empty] | QA |  | 1440 |  |  |  | 1300
[12 empty] | BA |  | 600 |  |  |  | 600
[12 empty] | Training |  | 160 | iteration 4 -5 |  |  | 160
[12 empty] | Total |  | 6384 |  | 55 | 351120 | 5964
Note on A9: The category to which this story belongs, if any.
Note on B9: The category to which this story belongs, if any.
Note on D9: If known, the Track that will deliver this story.
Note on E9: The Tech Story Points associated with this story. This value is translated into ABP/HP through velocity.

## Break OUt
Estimated 1 Point
Low | 16
High | 32
Total Points | 236
Low | 3776
High | 7552
Average | 5664
Our Points |  | Estimated Points
Point | Hours | Points | Hours
1 | 4 | 1 | 16
2 | 8 | 2 | 32
3 | 16 | 3 | 48
5 | 30 | 4 | 64
8 | 40 | 5 | 80 | [8 empty] | average | 3120 | #REF! |  |  | 12 weeks | 4 weeks
Track Total Hours
LOE in Hours Calculated
| Req # | Story # | Epic | User Story |  | Iteration | Our Points | Points | Low | High | Average | UX Priority | Eng Priority | Dependency | Notes |  | Low | High | High | High | High |  | Low | Low | Low | Low | Low |  | Avg | Avg | Avg | Avg | Avg
[5 empty] | Possible solution | [11 empty] | 1 | 2 | 3 | 4 | 5 |  | 1 | 2 | 3 | 4 | 5 |  | 1 | 2 | 3 | 4 | 5
|  | 1 | Community Site | Home page - Logged in/Logged out(Hero image, articles, QA activity, Twitter feed, total members) |  | 1 | 0 | 8 | 128 | 256 | 192 | 1 |  |  |  |  | 128 | 0 | 0 | 0 | 0 |  | 128 | 0 | 0 | 0 | 0 |  | 192 | 0 | 0 | 0 | 0
|  | 1.1 | Community Site | Community Header |  | 1 | 3
|  | 1.2 | Community Site | Community Global Navigation | WP Menus | 1 | 3 |  | 128
|  | 100 | Home Page | See all Experts (we are here to help) | http://blog.fitstudio.com/ - Blog Contributors | 1 | 3
|  | 100.1 | Home Page | Featured Blog | FA Lite - plugin | 1 | 3
|  | 100.2 | Home Page | Ask A Question | custom | 1 | 5
|  | 100.3 | Home Page | Featured Q&A | Widget by categories | 1 | 3
|  | 100.4 | Home Page | Poll of the week | Iteration 4 | 1 | 0
|  | 100.5 | Home Page | Add Unit | CQ5, iteration 4 | 1 | 0
|  | 100.6 | Home Page | Recent Activity | by asking, answering and following content | 1 | 3
|  | 1.3 | Community Site | Community Footer |  | 1 | 3
| Tim | 100.7 | Home Page | FED |  | 1 | 40 | 12 | 192 | 384 | 288 | 2 |  |  |  |  | 192 | 0 | 0 | 0 | 0 |  | 192 | 0 | 0 | 0 | 0 |  | 288 | 0 | 0 | 0 | 0
|  | 2 | Community Site | Q & A (discussions) |  | 1 | 0 | 8 | 128 | 0 | 64 | 2 |  |  | (CPT) Custom Post Type post_type=question as a parent parent_post=0. (CPT) post_type=answer, parent_post={questionID} |  | 128 | 0 | 0 | 0 | 0 |  | 128 | 0 | 0 | 0 | 0 |  | 64 | 0 | 0 | 0 | 0
| Eddie | 2.1 | Q And A | Architect | wp_posts.post_type index field for searching | 1 | 2
|  | 2.2 | Q And A | Question = Post | SSO users are asking questions | 1 | 3
|  | 2.2 | Q And A | Comment = Answer | Nesting comments | 1 | 3
| Tim | 2.2 | Q And A | FED |  | 1 | 11 | 4 | 64 | 128 | 96 | 2
|  | 3 | Community Site | Blog |  | 1 | 0 | 3 | 48 | 96 | 72 | 1 |  |  | templates = single, archive, aside for video |  | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
|  | 3.1 | Blog | 404 |  | 1 | 3
|  | 3.2 | Blog | Archvie | Includes, tags, category, search results | 1 | 3
|  | 3.3 | Blog | Single |  | 1 | 3
|  | 3.4 | Blog | Page | This goes to interest and customer service | 1 | 0
|  | 3.5 | Blog | FED |  | 1 | 48 | 10 | 160 | 320 | 240 | 1
|  | 4 | User Profile | User profile page (My discussions, photo, Interests, badges) |  | 1 | 0 | 5 | 80 | 160 | 120 | 2 |  |  |  |  | 80 | 0 | 0 | 0 | 0 |  | 80 | 0 | 0 | 0 | 0 |  | 120 | 0 | 0 | 0 | 0
| Jason | 4.1 | User Profile | Dashboard |  | 1 | 5
| Jason | 4.2 | User Profile | My Discussions & Answers |  | 1 | 3
| Jason | 4.3 | User Profile | My Following |  | 1 | 3
| Jason | 4.4 | User Profile | Change My Setting | Unfollow and stopping emails | 1 | 2
| Jason | 4.5 | User Profile | My Votes |  | 1 | 2
| Jason | 4.6 | User Profile | My Flags |  | 1 | 2
|  | 4.7 | User Profile | FED |  | 1 | 48 | 16 | 256 | 512 | 384 | 2
|  | 5 | Community Site | User Admin Settings Page |  | 1 | 8 | 3 | 48 | 96 | 72 | 4 |  |  | Place where they can turn off (opt-out) of following |  | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
|  | 6 | Community Site | Articles (Guides) |  | 1 | 3 | 2 | 32 | 64 | 48 | 3 |  |  |  |  | 32 | 0 | 0 | 0 | 0 |  | 32 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0
|  | 7 | Community Site | Ad units on pages |  | 4 | 16 | 5 | 80 | 160 | 120 | 0 |  |  | Use CQ5 |  | 0 | 0 | 0 | 160 | 0 |  | 0 | 0 | 0 | 80 | 0 |  | 0 | 0 | 0 | 120 | 0
|  | 8 | Community Site | Site search (discussions, articles, blogs) |  | 1 | 8 | 3 | 48 | 96 | 72 | 3 |  |  | Indexing of blog and store pages is new addition. |  | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
|  | 9 | Search | Site Search - Auto Complete |  | 5 | 0 | 8 | 128 | 256 | 192 | 0 |  |  | will require mongo DB |  | 0 | 0 | 0 | 0 | 256 |  | 0 | 0 | 0 | 0 | 128 |  | 0 | 0 | 0 | 0 | 192
|  | 9.1 | Search | Mongo DB setup |  |  | 8
|  | 9.2 | Search | Code Integration |  |  | 8
|  | 9.3 | Search | Jquery |  |  | 8
|  | 9.4 | Search | Stress testing |  |  | 3
|  | 9.5 | Search | FED |  | 1 | 13 | 4 | 64 | 128 | 96 | 0
| Brian/Dan | 10 | Community Site | SSO |  | 1 | 0 | 5 | 80 | 160 | 120 | 0 |  |  | Profile/SSO will take care of validating and authenticating open id just like user/password |  | 80 | 0 | 0 | 0 | 0 |  | 80 | 0 | 0 | 0 | 0 |  | 120 | 0 | 0 | 0 | 0
| Brian/Dan | 10.1 | Login | SSO |  |  | 8
| Brian/Dan | 10.2 | Login | Open ID - Facebook |  |  | 8
| Brian/Dan | 10.3 | Login | Create Login |  |  | 5
| Brian/Dan | 10.4 | Login | Integration / Security |  |  | 3
| Brian/Dan | 11 | Community Site | User Login |  | 1 | 0 | 5 | 80 | 160 | 120 | 2 |  |  |  |  | 80 | 0 | 0 | 0 | 0 |  | 80 | 0 | 0 | 0 | 0 |  | 120 | 0 | 0 | 0 | 0
| Brian/Dan | 11.1 | Login | User Login |  |  | 2
| Brian/Dan | 11.2 | Login | Login/ Logout |  |  | 2
| Brian/Dan | 11.3 | Login | FED |  | 1 | 40 | 12 | 192 | 384 | 288 | 2
| Sebastian | 12 | Community Site | Feedback (Qualtrics) |  | 3 | 5 | 1 | 16 | 32 | 24 | 0 |  |  |  |  | 0 | 0 | 32 | 0 | 0 |  | 0 | 0 | 16 | 0 | 0 |  | 0 | 0 | 24 | 0 | 0
| Tim/Jason | 13 | Community Site | Contacts page |  | 1 | 3 | 1 | 16 | 32 | 24 | 5 |  |  |  |  | 16 | 0 | 0 | 0 | 0 |  | 16 | 0 | 0 | 0 | 0 |  | 24 | 0 | 0 | 0 | 0
|  | 14 | Community Site | Tag/filter content |  | 1 | 0 | 8 | 128 | 256 | 192 | 2 |  |  | Separate installation for each site. Double UX work |  | 128 | 0 | 0 | 0 | 0 |  | 128 | 0 | 0 | 0 | 0 |  | 192 | 0 | 0 | 0 | 0
|  | 15 | User Profile | Activity feed based on profile |  | 1 | 8 | 3 | 48 | 96 | 72 | 0 |  |  | Logic to aggregate data based on profile interest settings. |  | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
|  | 16 | Community Site | Voting and Flagging |  | 4 | 0 | 2 | 32 | 64 | 48 | 3 |  |  |  |  | 0 | 0 | 0 | 64 | 0 |  | 0 | 0 | 0 | 32 | 0 |  | 0 | 0 | 0 | 48 | 0
| Tim | 16.1 | Voting And Flagging | Voting and Flagging |  |  | 3
| tim | 16.2 | Voting And Flagging | AJAX Jquery |  |  | 3
| Brian | 16.3 | Voting And Flagging | API end point vote |  |  | 2
| Brian | 16.4 | Voting And Flagging | API end point flagging |  |  | 2
|  | 17 | Community Site | Share it functionality(discussion, articles) |  | 2 | 0 | 2 | 32 | 64 | 48 | 1 |  |  | Add This |  | 0 | 64 | 0 | 0 | 0 |  | 0 | 32 | 0 | 0 | 0 |  | 0 | 48 | 0 | 0 | 0
| Jason | 17.1 | Share It | FED |  |  | 3
| Jason | 17.2 | Share It | Templetes |  |  | 5
|  | 18 | Community site | Emails Responsys Integration |  | 3 | 0 | 5 | 80 | 160 | 120 | 10 |  |  | Integration with responsys |  | 0 | 0 | 160 | 0 | 0 |  | 0 | 0 | 80 | 0 | 0 |  | 0 | 0 | 120 | 0 | 0
| Dan | 18.1 | Responsys | Collect User Data to triggering emails (see user profile) |  |  | 8
| Dan | 18.2 | Responsys | Cron to send to responsys |  |  | 8
| Dan | 18.3 | Responsys | Daily Cron |  |  | 8
| Sebastian | 19 | Community site | Google analytics |  | 1 | 3 | 1 | 16 | 32 | 24 | 0 |  |  |  |  | 16 | 0 | 0 | 0 | 0 |  | 16 | 0 | 0 | 0 | 0 |  | 24 | 0 | 0 | 0 | 0
| Sebastian | 20 | Community site | Prafanity filter | spike story talk to pavan. Brendan | 2 | 8 | 2 | 32 | 64 | 48 | 0 |  |  |  |  | 0 | 64 | 0 | 0 | 0 |  | 0 | 32 | 0 | 0 | 0 |  | 0 | 48 | 0 | 0 | 0
|  | 21 | Community site | Interest Page - Customer Service |  | 1 | 0 | 5 | 80 | 160 | 120 | 0 |  |  |  |  | 80 | 0 | 0 | 0 | 0 |  | 80 | 0 | 0 | 0 | 0 |  | 120 | 0 | 0 | 0 | 0
|  | 21.1 | Customer Service Page | See Home |  |  | 8
|  | 21.2 | Customer Service Page | Build None Home Page items |  |  | 8
|  | 22 | Community site | Interest Page - 2 Category Template Page |  | 1 | 0 | 3 | 48 | 96 | 72 | 0 |  |  |  |  | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
| Jason/Tim | 22.1 | Interest Page | Template A |  |  | 5
| Jason/Tim | 22.2 | Interest Page | Template B |  |  | 5
|  | 22.3 | Interest Page | FED |  | 1 | 0 | 4 | 64 | 128 | 96 | 0
| Jason | 23 | Community site | Comments (Blogs, Articles) |  | 1 | 3 | 1 | 16 | 32 | 24 | 6 |  |  |  |  | 16 | 0 | 0 | 0 | 0 |  | 16 | 0 | 0 | 0 | 0 |  | 24 | 0 | 0 | 0 | 0
|  | 24 | Migration | Migrate forums |  | 1 | 16 | 5 | 80 | 160 | 120 | 0 |  |  | View Points provides conversion data |  | 80 | 0 | 0 | 0 | 0 |  | 80 | 0 | 0 | 0 | 0 |  | 120 | 0 | 0 | 0 | 0
|  | 25 | Migration | Migrate articles |  | 2 | 8 | 3 | 48 | 96 | 72 | 0 |  |  | View Points provides conversion data |  | 0 | 96 | 0 | 0 | 0 |  | 0 | 48 | 0 | 0 | 0 |  | 0 | 72 | 0 | 0 | 0
|  | 26 | Migration | Migrate blogs |  | 2 | 8 | 3 | 48 | 96 | 72 | 0 |  |  | View Points provides conversion data |  | 0 | 96 | 0 | 0 | 0 |  | 0 | 48 | 0 | 0 | 0 |  | 0 | 72 | 0 | 0 | 0
|  | 27 | Migration | Migrate User Info |  | 2 | 16 | 5 | 80 | 160 | 120 | 0 |  |  | View Points provides conversion data |  | 0 | 160 | 0 | 0 | 0 |  | 0 | 80 | 0 | 0 | 0 |  | 0 | 120 | 0 | 0 | 0
|  | 28 | Migration | Search index all migrated contents |  | 3 | 16 | 5 | 80 | 160 | 120 | 0 |  |  | View Points provides conversion data |  | 0 | 0 | 160 | 0 | 0 |  | 0 | 0 | 80 | 0 | 0 |  | 0 | 0 | 120 | 0 | 0
| Jason | 29 | Misc | Setup data & taxonomy | Hamid | 1 | 24 | 8 | 128 | 256 | 192 | 1 |  |  | This is step1 before building any functionality. |  | 128 | 0 | 0 | 0 | 0 |  | 128 | 0 | 0 | 0 | 0 |  | 192 | 0 | 0 | 0 | 0
|  | 30 | Misc | Support old URL's redirects | Follow Up Brendan | 1 | 24 | 8 | 128 | 256 | 192 | 0 |  |  | Create support for OLD URL's toredirect to the new site URL's |  | 128 | 0 | 0 | 0 | 0 |  | 128 | 0 | 0 | 0 | 0 |  | 192 | 0 | 0 | 0 | 0
| Sebastian | 31 | Misc | Architecture |  | 3 | 8 | 5 | 80 | 160 | 120 | 0 |  |  | Server setup. Cacheing |  | 0 | 0 | 160 | 0 | 0 |  | 0 | 0 | 80 | 0 | 0 |  | 0 | 0 | 120 | 0 | 0
| Sebastian | 32 | Misc | Setup environments (Dev,QA,integration,Prod) |  | 1 | 8 | 3 | 48 | 96 | 72 | 0 |  |  |  |  | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
| Sebastian | 33 | Misc | Performance testing |  | 1 | 8 | 3 | 48 | 96 | 72 | 0 |  |  |  |  | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
| Sebastian | 34 | Misc | Continous integration environment |  | 1 | 3 | 1 | 16 | 32 | 24 | 0 |  |  |  |  | 16 | 0 | 0 | 0 | 0 |  | 16 | 0 | 0 | 0 | 0 |  | 24 | 0 | 0 | 0 | 0
| Sebastian | 35 | Misc | Iterative production releases 1 |  | 1 | 3 | 1 | 16 | 32 | 24 | 0 |  |  |  |  | 16 | 0 | 0 | 0 | 0 |  | 16 | 0 | 0 | 0 | 0 |  | 24 | 0 | 0 | 0 | 0
| Sebastian | 36 | Misc | Iterative production releases 2 |  | 2 | 3 | 1 | 16 | 32 | 24 | 0 |  |  |  |  | 0 | 32 | 0 | 0 | 0 |  | 0 | 16 | 0 | 0 | 0 |  | 0 | 24 | 0 | 0 | 0
| Sebastian | 37 | Misc | Iterative production releases 3 |  | 3 | 3 | 1 | 16 | 32 | 24 | 0 |  |  |  |  | 0 | 0 | 32 | 0 | 0 |  | 0 | 0 | 16 | 0 | 0 |  | 0 | 0 | 24 | 0 | 0
| Sebastian | 38 | Misc | Iterative production releases 4 |  | 4 | 3 | 1 | 16 | 32 | 24 | 0 |  |  |  |  | 0 | 0 | 0 | 32 | 0 |  | 0 | 0 | 0 | 16 | 0 |  | 0 | 0 | 0 | 24 | 0
| Sebastian | 39 | Misc | Iterative production releases 5 |  | 5 | 3 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 40 | Misc | Meetings Iteration 1 |  | 1 | 8 | 2 | 32 | 64 | 48 | 0 |  |  |  |  | 32 | 0 | 0 | 0 | 0 |  | 32 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0
|  | 41 | Misc | Meetings Iteration 2 |  | 2 | 8 | 2 | 32 | 64 | 48 | 0 |  |  |  |  | 0 | 64 | 0 | 0 | 0 |  | 0 | 32 | 0 | 0 | 0 |  | 0 | 48 | 0 | 0 | 0
|  | 42 | Misc | Meetings Iteration 3 |  | 3 | 8 | 2 | 32 | 64 | 48 | 0 |  |  |  |  | 0 | 0 | 64 | 0 | 0 |  | 0 | 0 | 32 | 0 | 0 |  | 0 | 0 | 48 | 0 | 0
|  | 43 | Misc | Meetings Iteration 4 |  | 4 | 8 | 2 | 32 | 64 | 48 | 0 |  |  |  |  | 0 | 0 | 0 | 64 | 0 |  | 0 | 0 | 0 | 32 | 0 |  | 0 | 0 | 0 | 48 | 0
|  | 44 | Misc | Meetings Iteration 5 |  | 5 | 8 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
|  | 45 | Admin/moderation | Display flagged content & delete inappropriate entries(coments, questions) |  | 1 | 8 | 3 | 48 | 96 | 72 | 6 |  |  |  |  | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
|  | 46 | Admin/moderation | Ldap login |  | 1 |  | 1 | 16 | 32 | 24 | 6 |  |  |  |  | 16 | 0 | 0 | 0 | 0 |  | 16 | 0 | 0 | 0 | 0 |  | 24 | 0 | 0 | 0 | 0
| Sebastian |  | LDAP Login | Talks to Meeks |  |  | 3
| Jason |  | LDAP Login | FED Work (update WP-Admin |  |  | 3
|  | 47 | Admin/moderation | Reporting |  | 4 | 8 | 2 | 32 | 64 | 48 | 6 |  |  |  |  | 0 | 0 | 0 | 64 | 0 |  | 0 | 0 | 0 | 32 | 0 |  | 0 | 0 | 0 | 48 | 0
|  | 48 | Home Page | Home page content mgmt. |  | 1 | 8 | 3 | 48 | 96 | 72 | 6 |  |  | Hero Image, Featured Article - (FA Lite) |  | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
|  | 49 | CMS | Author buying guides | Any sort of admin work | 1 | 3 | 1 | 16 | 32 | 24 | 6 |  |  |  |  | 16 | 0 | 0 | 0 | 0 |  | 16 | 0 | 0 | 0 | 0 |  | 24 | 0 | 0 | 0 | 0
|  | 50 | CMS | Author blogs | Any sort of admin work | 1 | 8 | 3 | 48 | 96 | 72 | 6 |  |  |  |  | 48 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
|  | 51 | CMS | Experts Q & A | Any sort of admin work | 1 | 24 | 8 | 128 | 256 | 192 | 6 |  |  |  |  | 128 | 0 | 0 | 0 | 0 |  | 128 | 0 | 0 | 0 | 0 |  | 192 | 0 | 0 | 0 | 0
|  | 52 | Feeds | Syndication | ?? | 3 |  | 3 | 48 | 96 | 72 | 0 |  |  |  |  | 0 | 0 | 96 | 0 | 0 |  | 0 | 0 | 48 | 0 | 0 |  | 0 | 0 | 72 | 0 | 0
|  | 58 | Community Site | Manuals | 200 hours | 5 |  | 8 | 128 | 256 | 192 | 0
|  | 59 | Community Site | Following |  | 2 | 8 | 2 | 32 | 64 | 48 | 0
|  | 60 | Community Site | Polls |  | 4 | 13 | 3 | 48 | 96 | 72 | 0
[17 empty] | Low | High | High | High | High |  | Low | Low | Low | Low | Low |  | Avg | Avg | Avg | Avg | Avg
[6 empty] | Totals |  | 249 | 4112 | 7712 | 5848 |  |  |  |  | Total Hours | 2016 | 576 | 704 | 384 | 256 |  | 2016 | 288 | 352 | 192 | 128 |  | 2896 | 432 | 528 | 288 | 192
[16 empty] | Weeks | 56 | 16 | 19.5556 | 10.6667 | 7.1111 |  | 56 | 8 | 9.7778 | 5.3333 | 3.5556 |  | 80.4444 | 12 | 14.6667 | 8 | 5.3333
[16 empty] | Actual Weeks | 12 | 3 | 3 | 3 | 3 |  | 12 | 3 | 3 | 3 | 3 |  | 12 | 3 | 3 | 3 | 3
[16 empty] | # of Dev | 4.6667 | 5.3333 | 6.5185 | 3.5556 | 2.3704 |  | 4.6667 | 2.6667 | 3.2593 | 1.7778 | 1.1852 |  | 6.7037 | 4 | 4.8889 | 2.6667 | 1.7778
[16 empty] | Grand Total Hours |  |  |  |  | 3936 | [6 empty] | 2976 |  |  |  |  | 4336
[16 empty] | Iteration 1 | low | 2016 |  |  |  | 2016
[16 empty] | Iteration 2-4 | avg | 1440 |  |  |  | 1600
[16 empty] | QA |  | 1160 |  |  |  | 1300
[16 empty] | BA |  | 600 |  |  |  | 600
[16 empty] | Training |  | 160 | iteration 4 -5 |  |  | 160
[16 empty] | Total |  | 5216 |  | 55 | 286880 | 5676
Note on B20: The category to which this story belongs, if any.
Note on C20: The category to which this story belongs, if any.
Note on D20: The category to which this story belongs, if any.
Note on G20: If known, the Track that will deliver this story.
Note on I20: The Tech Story Points associated with this story. This value is translated into ABP/HP through velocity.

## Risks
Item | Risk | Dependency
1 | Tight deadline because of View Points Contract | View Points
2 | Migration | View Points
3 | Late UX handoffs | UX
4 | Communities mysears.com/mykmart.com dependency. This could become big
5 | Sears Single Sign-On (SSO) | ENG
6 | LDAP | ENG

## Assumptions
Item | Assumption
1 | Migration off of view points is the overall strategic plan
2 | Question and Answers it the most important business objective
3 | Migration: Prerequisite: provide mapping of viewpoints category to new community platform categories/taxonomy. Low - them create a file dump via WXR, Medium - some exporter, High - custom batch. multiple files
4 | Design is satisfactory to the team.
5 | Code is reviewed.
6 | Story acceptance criteria is met.
7 | No p1 and p2 open jira's.
8 | QA/BA accepted/passed the story.