## Estimate v2
|  | Total points | 174 |  | Hours per point |  |  |  | weeks | 12 |  |  | Brian
[5 empty] | Low | Hi |  |  | week hours | 36 |  |  | Sebastian
|  | Total Hrs (High) | 5568 | Best quality | 16 | 32 |  |  | Total Hours | 432 |  |  | Dan
|  | Total Hrs (Average) | 4176 | Moderate |  |  |  |  | low | 2080 | 4.8148
|  | Total Hrs Low) | 2784 | Aggressive |  |  |  |  | high | 4160 | 9.6296
[9 empty] | average | 3120 | 7.2222 |  |  |  | 12 weeks | 4 weeks
Track Total Hours
LOE in Hours Calculated
Req # | Story # | Epic | User Story | Release | Points | Low | High | Average | UX Priority | Eng Priority | Dependency | Notes |  |  | Low | High | High | High | High | Low | Low | Low | Low | Low |  | Avg | Avg | Avg | Avg | Avg
[15 empty] | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 |  | 1 | 2 | 3 | 4 | 5
| 1 | Community Site | Home page - Logged in/Logged out(Hero image, articles, QA activity, Twitter feed, total members) | 1 | 8 | 128 | 256 | 192 | 1 | [5 empty] | 128 | 0 | 0 | 0 | 0 | 128 | 0 | 0 | 0 | 0 |  | 192 | 0 | 0 | 0 | 0
| 2 | Community Site | Q & A (discussions) | 1 | 8 | 128 | 256 | 192 | 2 |  |  | (CPT) Custom Post Type post_type=question as a parent parent_post=0. (CPT) post_type=answer, parent_post={questionID} |  |  | 128 | 0 | 0 | 0 | 0 | 128 | 0 | 0 | 0 | 0 |  | 192 | 0 | 0 | 0 | 0
| 3 | Community Site | Blog | 1 | 3 | 48 | 96 | 72 | 1 |  |  | templates = single, archive, aside for video |  |  | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
| 4 | Community Site | User profile page (My discussions, photo, Interests, badges) | 1 | 5 | 80 | 160 | 120 | 2 | [5 empty] | 80 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 |  | 120 | 0 | 0 | 0 | 0
| 5 | Community Site | User Admin Settings Page | 1 | 3 | 48 | 96 | 72 | 4 |  |  | Place where they can turn off (opt-out) of following |  |  | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
| 6 | Community Site | Articles (Guides) | 1 | 2 | 32 | 64 | 48 | 3 | [5 empty] | 32 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0
| 7 | Community Site | Ad units on pages | 3 | 5 | 80 | 160 | 120 | 0 |  |  | Use CQ5 |  |  | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 80 | 0 | 0 |  | 0 | 0 | 120 | 0 | 0
| 8 | Community Site | Site search (discussions, articles, blogs) | 1 | 3 | 48 | 96 | 72 | 3 |  |  | Indexing of blog and store pages is new addition. |  |  | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
| 9 | Community Site | Site Search - Auto Complete | 4 | 8 | 128 | 256 | 192 | 0 |  |  | will require mongo DB |  |  | 0 | 0 | 0 | 256 | 0 | 0 | 0 | 0 | 128 | 0 |  | 0 | 0 | 0 | 192 | 0
| 10 | Community Site | SSO | 1 | 5 | 80 | 160 | 120 | 0 |  |  | Profile/SSO will take care of validating and authenticating open id just like user/password |  |  | 80 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 |  | 120 | 0 | 0 | 0 | 0
| 11 | Community Site | User Login | 1 | 5 | 80 | 160 | 120 | 2 | [5 empty] | 80 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 |  | 120 | 0 | 0 | 0 | 0
| 12 | Community Site | Feedback (Qualtrics) | 3 | 1 | 16 | 32 | 24 | 0 | [5 empty] | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 16 | 0 | 0 |  | 0 | 0 | 24 | 0 | 0
| 13 | Community Site | Contacts page | 1 | 1 | 16 | 32 | 24 | 5 | [5 empty] | 16 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 |  | 24 | 0 | 0 | 0 | 0
| 14 | Community Site | Tag/filter content by site (mysears/mykmart) | 1 | 8 | 128 | 256 | 192 | 2 |  |  | Separate installation for each site. Double UX work |  |  | 128 | 0 | 0 | 0 | 0 | 128 | 0 | 0 | 0 | 0 |  | 192 | 0 | 0 | 0 | 0
| 15 | Community Site | Activity feed based on profile | 1 | 3 | 48 | 96 | 72 | 0 |  |  | Logic to aggregate data based on profile interest settings. |  |  | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
| 16 | Community Site | Flag user added content(comments, discussions) | 2 | 2 | 32 | 64 | 48 | 3 | [5 empty] | 0 | 64 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  | 0 | 48 | 0 | 0 | 0
| 17 | Community Site | Share it functionality(discussion, articles) | 2 | 2 | 32 | 64 | 48 | 1 |  |  | Add This |  |  | 0 | 64 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  | 0 | 48 | 0 | 0 | 0
| 18 | Community site | Emails Responsys Integration | 3 | 5 | 80 | 160 | 120 | 10 |  |  | Integration with responsys |  |  | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 80 | 0 | 0 |  | 0 | 0 | 120 | 0 | 0
| 19 | Community site | Google analytics | 1 | 1 | 16 | 32 | 24 | 0 | [5 empty] | 16 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 |  | 24 | 0 | 0 | 0 | 0
| 20 | Community site | Prafanity filter | 2 | 2 | 32 | 64 | 48 | 0 | [5 empty] | 0 | 64 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  | 0 | 48 | 0 | 0 | 0
| 21 | Community site | Interest Page - Customer Service | 1 | 5 | 80 | 160 | 120 | 0 | [5 empty] | 80 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 |  | 120 | 0 | 0 | 0 | 0
| 22 | Community site | Interest Page - 2 Category Template Page | 1 | 3 | 48 | 96 | 72 | 0 | [5 empty] | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
| 23 | Community site | Comments (Blogs, Articles) | 1 | 1 | 16 | 32 | 24 | 6 | [5 empty] | 16 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 |  | 24 | 0 | 0 | 0 | 0
| 24 | Migration | Migrate forums | 1 | 5 | 80 | 160 | 120 | 0 |  |  | View Points provides conversion data |  |  | 80 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 |  | 120 | 0 | 0 | 0 | 0
| 25 | Migration | Migrate articles | 2 | 3 | 48 | 96 | 72 | 0 |  |  | View Points provides conversion data |  |  | 0 | 96 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 |  | 0 | 72 | 0 | 0 | 0
| 26 | Migration | Migrate blogs | 2 | 3 | 48 | 96 | 72 | 0 |  |  | View Points provides conversion data |  |  | 0 | 96 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 |  | 0 | 72 | 0 | 0 | 0
| 27 | Migration | Migrate User Info | 2 | 5 | 80 | 160 | 120 | 0 |  |  | View Points provides conversion data |  |  | 0 | 160 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 |  | 0 | 120 | 0 | 0 | 0
| 28 | Migration | Search index all migrated contents | 3 | 5 | 80 | 160 | 120 | 0 |  |  | View Points provides conversion data |  |  | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 80 | 0 | 0 |  | 0 | 0 | 120 | 0 | 0
| 29 | Misc | Setup data & taxonomy | 1 | 8 | 128 | 256 | 192 | 1 |  |  | This is step1 before building any functionality. |  |  | 128 | 0 | 0 | 0 | 0 | 128 | 0 | 0 | 0 | 0 |  | 192 | 0 | 0 | 0 | 0
| 30 | Misc | Support old URL's redirects | 1 | 8 | 128 | 256 | 192 | 0 |  |  | Create support for OLD URL's toredirect to the new site URL's |  |  | 128 | 0 | 0 | 0 | 0 | 128 | 0 | 0 | 0 | 0 |  | 192 | 0 | 0 | 0 | 0
| 31 | Misc | Architecture | 1 | 5 | 80 | 160 | 120 | 0 |  |  | Server setup. Cacheing |  |  | 80 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 |  | 120 | 0 | 0 | 0 | 0
| 32 | Misc | Setup environments (Dev,QA,integration,Prod) | 1 | 3 | 48 | 96 | 72 | 0 | [5 empty] | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
| 33 | Misc | Performance testing | 1 | 3 | 48 | 96 | 72 | 0 | [5 empty] | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
| 34 | Misc | Continous integration environment | 1 | 1 | 16 | 32 | 24 | 0 | [5 empty] | 16 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 |  | 24 | 0 | 0 | 0 | 0
| 35 | Misc | Iterative production releases 1 | 1 | 1 | 16 | 32 | 24 | 0 | [5 empty] | 16 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 |  | 24 | 0 | 0 | 0 | 0
| 36 | Misc | Iterative production releases 2 | 2 | 1 | 16 | 32 | 24 | 0 | [5 empty] | 0 | 32 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 |  | 0 | 24 | 0 | 0 | 0
| 37 | Misc | Iterative production releases 3 | 3 | 1 | 16 | 32 | 24 | 0 | [5 empty] | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 16 | 0 | 0 |  | 0 | 0 | 24 | 0 | 0
| 38 | Misc | Iterative production releases 4 | 4 | 1 | 16 | 32 | 24 | 0 | [5 empty] | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 16 | 0 |  | 0 | 0 | 0 | 24 | 0
| 39 | Misc | Iterative production releases 5 | 5 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| 40 | Misc | Meetings Iteration 1 | 1 | 2 | 32 | 64 | 48 | 0 | [5 empty] | 32 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 |  | 48 | 0 | 0 | 0 | 0
| 41 | Misc | Meetings Iteration 2 | 2 | 2 | 32 | 64 | 48 | 0 | [5 empty] | 0 | 64 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  | 0 | 48 | 0 | 0 | 0
| 42 | Misc | Meetings Iteration 3 | 3 | 2 | 32 | 64 | 48 | 0 | [5 empty] | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 32 | 0 | 0 |  | 0 | 0 | 48 | 0 | 0
| 43 | Misc | Meetings Iteration 4 | 4 | 2 | 32 | 64 | 48 | 0 | [5 empty] | 0 | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 32 | 0 |  | 0 | 0 | 0 | 48 | 0
| 44 | Misc | Meetings Iteration 5 | 5 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| 45 | Admin/moderation | Display flagged content & delete inappropriate entries(coments, questions) | 1 | 3 | 48 | 96 | 72 | 6 | [5 empty] | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
| 46 | Admin/moderation | Ldap login | 1 | 1 | 16 | 32 | 24 | 6 | [5 empty] | 16 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 |  | 24 | 0 | 0 | 0 | 0
| 47 | Admin/moderation | Reporting | 3 | 2 | 32 | 64 | 48 | 6 | [5 empty] | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 32 | 0 | 0 |  | 0 | 0 | 48 | 0 | 0
| 48 | CMS | Home page content mgmt. | 1 | 3 | 48 | 96 | 72 | 6 |  |  | Hero Image, Featured Article - (FA Lite) |  |  | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
| 49 | CMS | Author buying guides | 1 | 1 | 16 | 32 | 24 | 6 | [5 empty] | 16 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 |  | 24 | 0 | 0 | 0 | 0
| 50 | CMS | Author blogs | 1 | 3 | 48 | 96 | 72 | 6 | [5 empty] | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 |  | 72 | 0 | 0 | 0 | 0
| 51 | CMS | Experts Q & A | 1 | 8 | 128 | 256 | 192 | 6 | [5 empty] | 128 | 0 | 0 | 0 | 0 | 128 | 0 | 0 | 0 | 0 |  | 192 | 0 | 0 | 0 | 0
| 52 | Feeds | Syndication | 3 | 3 | 48 | 96 | 72 | 0 | [5 empty] | 0 | 0 | 96 | 0 | 0 | 0 | 0 | 48 | 0 | 0 |  | 0 | 0 | 72 | 0 | 0
| 53 | Resource | FED Iteration 1 | 1 | 40 | 640 | 1280 | 960 | 0 | [5 empty] | 640 | 0 | 0 | 0 | 0 | 640 | 0 | 0 | 0 | 0 |  | 960 | 0 | 0 | 0 | 0
| 54 | Resource | FED Iteration 2 | 2 | 15 | 240 | 480 | 360 | 0 | [5 empty] | 0 | 480 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 |  | 0 | 360 | 0 | 0 | 0
| 55 | Resource | FED Iteration 3 | 3 | 5 | 80 | 160 | 120 | 0 | [5 empty] | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 80 | 0 | 0 |  | 0 | 0 | 120 | 0 | 0
| 56 | Resource | FED Iteration 4 | 4 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| 57 | Resource | FED Iteration 5 | 5 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
[15 empty] | Low | High | High | High | High | Low | Low | Low | Low | Low |  | Avg | Avg | Avg | Avg | Avg
|  |  |  | Totals | 234 | 3744 | 7488 | 5616 | [5 empty] | Total Hours | 2544 | 1120 | 928 | 352 | 0 | 2544 | 560 | 464 | 176 | 0 |  | 3816 | 840 | 576 | 264 | 0
[14 empty] | Weeks | 70.6667 | 31.1111 | 25.7778 | 9.7778 | 0 | 70.6667 | 15.5556 | 12.8889 | 4.8889 | 0 |  | 106 | 23.3333 | 16 | 7.3333 | 0
[14 empty] | Actual Weeks | 12 | 3 | 4 | 4 | 4 | 12 | 3 | 4 | 4 | 4 |  | 12 | 3 | 4 | 4 | 4
[14 empty] | # of Dev | 5.8889 | 10.3704 | 6.4444 | 2.4444 | 0 | 5.8889 | 5.1852 | 3.2222 | 1.2222 | 0 |  | 8.8333 | 7.7778 | 4 | 1.8333 | 0
[14 empty] | Grand Total Hours |  |  |  |  | 4944 | [5 empty] | 3744 |  |  |  |  | 5496
[14 empty] | Iteration 1 | low | 2544
[14 empty] | Iteration 2-4 | avg | 1680
[14 empty] | QA |  | 1400
[14 empty] | BA |  | 600
[14 empty] | Training |  | 160 | iteration 4 -5
[14 empty] | Total |  | 6224
Note on A9: The category to which this story belongs, if any.
Note on B9: The category to which this story belongs, if any.
Note on C9: The category to which this story belongs, if any.
Note on E9: If known, the Track that will deliver this story.
Note on F9: The Tech Story Points associated with this story. This value is translated into ABP/HP through velocity.

## Users
Req. # | Features | WP-Admin | Admin | Moderator | External User | Expert | Blogger
3.3 | CMS
3.3.1 | Homepage
| • Assign Admin rights • Inputs text for Promo in Nav bar • Add/remove content from or to each module |  | x | x
3.3.2 | Ad Management
| • Upload Ad Units • Designate Ad Unit Location • Remove Ad Units • Schedule Ad Units |  | x | x
3.3.3 | Image & Video Management
| • Store images & Videos to centralized location to upload to Blogs and etc. • Add or delete image and video tags • Email images from tool |  | x | x |  |  | x
| • Delete images and videos |  | x | x
3.3.4 | Blogs and Buying Guides
| • Preview, Draft, Cancel |  | x | x |  | x | x
| • Schedule and Publish |  | x
3.3.5 | Category Pages
| • Add, delete,and modify |  | x | x
3.4 | Moderation
3.4.1 | Profanity Filters |  | x
3.4.2 | Blog Comments |  | x | x |  |  | x
3.4.3 | Q&A Moderation
| • Close Comments • Reply/remove Answers • Move one Q&A from one topic to another • Designate answer as best answer |  | x | x
3.4.4 | Flagged for concern content
| • Flagged content w/reason by flagger |  | x | x |  | x | x
| • Review content (reject if violates, mark as review if not) |  | x | x
Polls
| • Add, review and remove Polls |  | x | x
3.5 | Internal Users
3.5.2 | Add users and assign roles |  | x
3.5.3 | Remove/modify user permissions |  | x
3.6 | Reports
3.7 | External Users
3.7.2 | • View Member information (delete account, assign roll and etc) |  | x | x
3.7.3 | • Assign Badges manually |  | x | x
3.8 | Emails
3.9 | Expert UI
3.9.1 | Questions from Queue |  | x | x |  | x
| Add Expert roll to a user |  | x | x
Ask question
Vote
Answer Question
Follow CAT/question/tag
Add and Delete Tags

## UX Estimates
Feature | UX Hours | Copy Hours | Creative Hours | FED Hours | Total Hours per feature
Q&A (3.5, 3.6) | 140 | 16 | 130 | 55.5 | 341.5
Search (3.3) | 200 | 10 | 120 | 57.5 | 387.5
Homepage (3.3, 3.4. 3.12) (Needs to go to Design Review) | 330 | 48 | 310 | 120 | 808
Blog (3.10) | 80 | 8 | 90 | 20 | 198
Interest Page (3.9, 3.10, 3.11) | 200 | 24 | 220 | 45 | 489
Login/Registration (3.1, 3.2) | 60 | 24 | 132 | 80 | 296
Profile (3.1, 3.2, 3.3, 3.7 (logged in state), 3.13, 3.17) | 180 | 76 | 582 | 252.5 | 1090.5
Admin & MOD Tool (?) | 464 |  |  | 359 | 823
Total | 1654 | 206 | 1584 | 989.5 | 4433.5

## Risks
Item | Risk | Dependency
1 | Tight deadline because of View Points Contract | View Points
2 | Migration | View Points
3 | Late UX handoffs | UX
4 | Communities mysears.com/mykmart.com dependency. This could become big
5 | Sears Single Sign-On (SSO) | ENG
6 | LDAP | ENG

## Assumptions
Item | Assumption
1 | Migration off of view points is the overall strategic plan
2 | Question and Answers it the most important business objective
3 | Migration: Prerequisite: provide mapping of viewpoints category to new community platform categories/taxonomy. Low - them create a file dump via WXR, Medium - some exporter, High - custom batch. multiple files
4 | Design is satisfactory to the team.
5 | Code is reviewed.
6 | Story acceptance criteria is met.
7 | No p1 and p2 open jira's.
8 | QA/BA accepted/passed the story.

## Team Sizing
[9 empty] | 2012-08-29 |  |  | 2012-08-07 | Main | Iteration 1 | 12
| DRAFT | [7 empty] | 2012-09-12 |  |  | 2012-08-28 | Migration/UAT | Iteration 2 | 3 | Not counting release week
Project Start | 2012-05-21 | [7 empty] | 2012-09-26 |  |  | 2012-09-25 |  | Iteration 3 | 4 | Not counting release week
Project End | 2012-10-24 | [7 empty] | 2012-10-10 |  |  | 2012-10-23 |  | Iteration 4 | 4 | Not counting release week
[9 empty] | 2012-10-24 |  |  |  |  | Iteration 5 |  | traingin
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | Total FTE
Location | Track | 2012-05-21 | 2012-05-28 | 2012-06-04 | 2012-06-11 | 2012-06-18 | 2012-06-25 | 2012-07-02 | 2012-07-09 | 2012-07-16 | 2012-07-23 | 2012-07-30 | 2012-08-06 | 2012-08-13 | 2012-08-20 | 2012-08-27 | 2012-09-03 | 2012-09-10 | 2012-09-17 | 2012-09-24 | 2012-10-01 | 2012-10-08 | 2012-10-15 | 2012-10-22 | 2012-10-29 | 2012-11-05 | 2012-11-12 | 2012-11-19 | 2012-11-26 | Staffing
Oversight Roles
0
| Tech Lead | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 140
| Tech Lead | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 140
| Architect | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 32
172
Total Oversight Person Hours |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 0 | 22 | 0 | 22 | 268
Team Roles
| Engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 520
| Eng, Web Developer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 30 | 30 | 30 | 30 | 180
| Eng, QA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 30 | 30 | 30 | 30 | 180
| Business Analyst | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
Total Team Person Hours |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 60 | 60 | 60 | 60 | 360
Grand Total Person Hours |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 82 | 82 | 60 | 82 | 60 | 82 | 628
352000
Roles | Skills | 2012-05-21: Exp. Yrs; 2012-05-28: Nbr; 2012-06-04: Onsite/Offshore
Project/technical lead | Agile development, Status reporting, Team management, Web development, Java, MySQL | 2012-05-21: 8; 2012-05-28: 1; 2012-06-04: SHI
Sr. Developer | Java 1.5, Web development, Spring, Spring MVC, MySQL, JPA/Hibernate/JDBC, Agile development | 2012-05-21: 8; 2012-05-28: 4; 2012-06-04: Onsite
Architect | Java 1.5, Web development, Spring, Spring MVC, MySQL, JPA/Hibernate/JDBC | 2012-05-21: 8; 2012-05-28: 1; 2012-06-04: SHI
Developer | Java 1.5, Web development, Spring, Spring MVC, MySQL, JPA/Hibernate.JDBC | 2012-05-21: 5'; 2012-05-28: 8; 2012-06-04: SHI
Sr QA |  | 2012-05-28: 2; 2012-06-04: Onsite
QA | Manual testing, JIRA | 2012-05-28: 2; 2012-06-04: SHI
Automation QA | Silenium or any other automation tool | 2012-05-28: 1; 2012-06-04: SHI
T Business Analyst |  | 2012-05-28: 1; 2012-06-04: Onsite
Note on A8: Enter all oversight roles with associated percentage allocation (0-1) for each week of the project.

## Release Dates
DRAFT
Iteration Plan
Iteration | Start | Days | End | Size | Status | Release Date | Goal | Release